## Slide 1
CIBC5022
Interpreting Site Reports
Lesson Site Plans and Details into MPP

## Slide 2
Kia ora and welcome
In this lesson, we’ll cover:
Examining reports appropriate to entering L2 Activities to MPP
Listing activities under the Building ie floors and walls
Listing activities for site itself
1
2
3
Programming For Construction

## Slide 3
Examining reports appropriate to entering L2 Activities to MPP
The Geotechnical Report
Footing Excavations
Foundations
Cross Bracing
Bearers
Joists
Blockwork
Key parts of the Geotechnical Report are contained in the summary and in the bore log appendices showing substrata at different depths. But all faces of the report should be read.

## Slide 4
Examining reports appropriate to entering L2 Activities to MPP
The Geotechnical Report - Conditoin

## Slide 5
Examining reports appropriate to entering L2 Activities to MPP
The Geotechnical Report - Condition

## Slide 6
Examining reports appropriate to entering L2 Activities to MPP
The Planning Report
Neighbours
Location
Area
Height
Appearance
Colour
Planting
Access
Hours of Operation
Look for any Conditions imposed by the TA (Territorial Authorities) You have 10 days to refuse to undertake these activities.

## Slide 7
Examining reports appropriate to entering L2 Activities to MPP
The Planning Report - Condition

## Slide 8
Examining reports appropriate to entering L2 Activities to MPP
The Planning Report - Condition

## Slide 9
Examining reports appropriate to entering L2 Activities to MPP
The Fire Report
Fire Appliance Access
Wall Linings and FRR materials
  30/30/30 with code
  60/60/60 with NZ Department of Education Schools
Distance from Boundary
Means of Escape
Fire Hose Reels
Alarm Sounding and press buttons
Electrical relay to main school warning systems
Evacuation Plan
  Clinic Warden
  Clinic Roster students and parents

## Slide 10
Examining reports appropriate to entering L2 Activities to MPP
The Fire Report - Conditions

## Slide 11
Examining reports appropriate to entering L2 Activities to MPP
The Fire Report - Conditions

## Slide 12
Examining reports appropriate to entering L2 Activities to MPP
The Traffic Report
Access to and From the Site
Parking and Ramp
The Topographical Report
Setting out the Geotechnical Bore Holes
Lists where any sumps or drains or rocks are
Lists any contamination for Orchids or Metals or Hydrocarbon
This is school for children therefore Geotechnical is extra necessary

## Slide 13
Examining reports appropriate to entering L2 Activities to MPP
The Traffic Report – Conditions

## Slide 14
Examining reports appropriate to entering L2 Activities to MPP
The Topographical Report

## Slide 15
Examining reports appropriate to entering L2 Activities to MPP
The Contract
Main Contract General Conditions NZS 3910; 2003
Special Conditions
Annex’s and Appendices
The Tender eg what the bid price was and how broken down
Exclusions eg if find rock client pays
Conditions for Timing

## Slide 16
Examining reports appropriate to entering L2 Activities to MPP
The Contract

## Slide 17
Examining reports appropriate to entering L2 Activities to MPP
The Contract

## Slide 18
Examining reports appropriate to entering L2 Activities to MPP
The Contract

## Slide 19
Examining reports appropriate to entering L2 Activities to MPP
The Building Consent
Lists the Waitakere City Council Building Inspector Inspections
Hours of Operation of Works – not before 7:30 AM and not after 7:30 PM
Any conditions accepted by the Contractor subsequent to consent being provided eg Use LVL timber; Use H6 Treated Piles; Use Window 1 mm Aluminium head flashings extending 100mm and cavity closers etc.

## Slide 20
- We will now enter the Work Breakdown Structure