Held 11:00 AM Friday the 7th August 2009 at Henderson Intermediate School

Meeting Agenda: 	Minutes of Last Meeting – N/A

Attendees:	Ray Allanson Support Manager ray.allanson@waitematadhb.govt.nz; Mob 021 241 8818

Dianne Houston Oral Dianne.Houston@waitematadhb.govt.nz; Mob 021 968 975

Rod Harvey PM Oral Health rodney.harvey@waitematadhb.govt.nz; Mob 021 659 382

Grant Brown MOE Network Facilitator grant.brown@minedu.govt.nz

Bruce Dale Principal Henderson Intermediate bruce.dale@hendersonint.school.nz

Colin Pauling Waitakere Architects colinp@waitakerearchitects.co.nz

Ron Crawford Henderson BOT starj@clear.net.nz

Sarah Jacobs Henderson BOT sarah.jacobs@hendersonint.school.nz

Joanne Carter Principal’s P.A joanne.carter@hendersonint.school.nz

Apologies	Belinda Tafua Dental Manager belinda.tafua@waitematadhb.govt.nz; Mob 021 467 163

Sandra Orr Team Leader School Network  sandra.orr@minedu.govt.nz; DDI 632 9373

Ray Webb Manager  raymond.webb@minedu.govt.nz; Mob 027 580 3071

Christina Jacobs HIS BOT Member christinajacobs12@gmail.com

Julie Owen HIS BOT Member julieo@westernheights.school.nz

Gerry Boortman HIS BOT Member gerry.boortman@stairs.co.nz

Minute Taker:	Rod Harvey

Item:		Comment:		Action By:	Date:

| 1. | Progress |  |  |
| --- | --- | --- | --- |
| 1.1 1.2 1.3 1.4 1.5 1.6 1.7 1.8 1.9 1.10 1.11 | Aim of the Meeting: Earlier the Henderson BOT had generally agreed the location of the new Dental Clinic and the new Gym off Fairdene Ave as shown on the Waitakere Architects plan “Proposed Gymnasium and Dental Clinic At Henderson Intermediate For the Board of Trustees Site Plan p101 Rev Ref 07-022”. The aim of the meeting now was now to discuss the clinic in more detail including access and timing relative to a new Dental Facility Lease. Location and Geotechnical Surveys; Prior to the meeting the WDHB Topographical and Geotechnical Surveys were undertaken to confirm suitability of the site above for the new 6-Chair fixed clinic. The site is suitable for WDHB. Lease Agreement Item 1; The new Dental Facility requires the drawing up of a Lease Agreement between the MOE and WDHB. That is, the lease would now be based upon the current BOT Architect’s Plan above, the Site Topographic Plan and WDHB 6 Chair Fixed Facility Generic Plans sent earlier to Waitakere Architects some of which were again tabled in the meeting as; - Community Oral Health Fixed Facilities Architectural Drawings cover perspective, - the Elevations and Sections Issue A Sheet A2 dated 7-10-08 - and Floor, Reflected Ceiling, Roof Framing, Finishes, Partition & Roof Plans Issue A Sheet A1 Dated 7-10-08 Lease Item 2 - Right of Way Traffic: The Right of Way from Fairdene Avenue requires a separation of vehicles from Children, particularly outgoing children ; WDHB will examine the traffic exits onto Fairdene with a Traffic Consultant including examining the suggestion to turn Edwards Road into a one way system with a left hand and right hand turn into Fairdene Ave only (and no left or right turns into Edwards from Fairdene). Lease Item 3 - Details of the Lease; Henderson School plans the modernisation of WC blocks in 2011 and the Clinic siting above will not impede this upgrade. Lease Item 4 - Proposed Clinic Power Gas and Communications Supply; WDHB will be looking to obtain services supplies to the new Clinic including Power, Water, Foul and Stormwater Drainage, Gas and Communications from Fairdene Avenue. Lease Item 5 - Proposed Schools Services Supply; However, it is understood that Henderson Int’ may be looking to future proof the current school’s power taken off Lincoln Road with a view to performing a transformer and cable supply upgrade and to better address future Loads. That is, if the School for example sees Natural Gas supply as desirable as an alternative to the current liquefied form it may be that shared power, gas and communications supply services for the Gym and the Clinic may be obtained by this route subject to agreeing load factors with Henderson Int. Henderson suggested WDHB contact Dennis Harry? Lease Item 6 - Fencing of the Clinic; The clinic will look at weighting visits out of pedestrian peak school entry and exit times - there still being vehicle traffic in this period along the ROW. The area of the Clinic will be fenced off from the school but not necessarily off from the Gym Carparking as the main aim of the fencing is to prevent spilling off into the school from the Clinic Area. Lease Item 7 - Concurrent Works on Site; The Meeting agreed that the Gym and the WDHB Clinic should proceed simultaneously if possible and that while the Gym and the Clinic shall be separate budgets - that subcontracting suppliers may be shared subject to programme, cost and performance. This will need further discussion. Site works, levels and drainage resolving the gyms and clinics Finished Floor Levels and overall services should be worked on together for both sites. Also, while the clinic may alter the current plans above, concrete floors cannot be ruled out. Lease Item 8 - Protected Tree: WDHB plan to retain the Puriri Tree to the East of the Clinic. Adjacent Classrooms may be removed at later phases in accordance with the Henderson BOT’s plan above. Lease Item 9 - Health and Safety; Health and Safety will be maintained on the clearly defined and fenced Clinic footprint following on from Possession by a Clinic Contractor. A Traffic Plan will be required for the ROW. WDHB will forward a Health and Safety plan to Henderson incorporating Henderson’s and WDHB’s health and safety procedures and plans where appropriate at Construction Licensing time. | 8th Aug WDHB WDHB MOE Hend Int WDHB Hend Int WDHB Hend Int WDHB WDHB WDHB Hend Int Note WDHB Hend Int |  |
| 2.0 | Contacts |  |  |
| 2.1 | Network Facilitator; Grant Brown Refer to contacts attached below | Note |  |
| 3.0 | Access |  |  |
| 3.1 | Classroom Replacement and New Build; The BOT see that providing WDHB with a clear site free of the current classrooms is desirable - (2x shown dotted adjacent and to South West of the proposed Clinic against the boundary and 2x shown in the middle of the proposed carparking plan). However, 2x of the classrooms must be reused and may cost upwards of $50K to relocate. It was agreed that the Grant Brown Network Facilitator look at the removal from site of the classrooms. WDHB offered to demolish. | Hend Int |  |
| 4.0 | Programme |  |  |
| 4.1 | Programme; Start on site before Christmas 09 is desirable by WDHB. | Note |  |
| 5.0 | Drawings |  |  |
| 5.1 | WDHB has a set of PDF drawings if required. | Note |  |
| 6.0 | Variations |  |  |
| 6.1 | NA |  |  |
| 7.0 | Health and Safety |  |  |
| 7.1 | See above as Lease Item | Note |  |
| 8.0 | General Items |  |  |
| 8.1 8.2 | Town Planning – WDHB plan to engage their Town Planning Consultant to issue a notice of advice to Waitakere of intentions with 20 days to respond. Construction License; Following the Lease Agreements completion the Construction Licence shall be required at the stage of Building Consent and prior to Construction award if possible – as per recent Dec’ 08 lease agreement advice document | WDHB WDHB |  |
| 9.0 | Next Meeting |  |  |
|  | RH of WDHB to arrange with Bruce Dale of Henderson Intermediate to go over draft Lease. | RH |  |
| 10.0 | Distribution to Contacts above |  |  |
| 10.1 | Contacts – See List appended below. (apologies for any errors at this early stage but aim is to develop a working Telephone and Contact List Document for WDHB and Henderson Int et al). | Note |  |

WDHB Oral Health New Clinical Facilities Roll Out Telephone List – General

| Name or Trade | Company | Address | Telephone | Mobile | Fax or Email Address |
| --- | --- | --- | --- | --- | --- |
| Carol Thomas | WDHB Service Manager |  |  | 021 879 361 |  |
| Belinda Tafua | WDHB Dental Manager |  |  | 021 467 163 |  |
| Ray Allanson | WDHB Support Services Manager |  |  | 021 241 8818 |  |
| Rod Harvey | WDHB Project Manager |  |  | 021 659 382 |  |
| Bruce Dale | Henderson Intermediate 6 Chair Phase 1 | 70 Lincoln Road; Waitakere City; | 09 838 8529 09 836 6932 |  | principal@hendersonint.school.nz admin@hendersonint.school.nz |
| Colin Pauling Architects | Waitakere Architects Ltd | Corner of Cabernet Crescent and Pinot Lane, Westgate 5C Pinot Lane, Massey, Waitakere 0614 | Tel 09 832 0435 Fax 09 832 0437 |  | www.waitakerearchitects.co.nz colin.p@waitakerearchitects.co.nz |
| Dr Kirsten Millar | Henderson North Dental School – Dental Ideas |  |  |  |  |
| Brian Flood | Wood and Partners |  | 09 571 2470 | 021 222 9797 | brian.flood@woods.co.nz |
| William Chung | Wood and Partners |  | 09 571 2470 | 027 226 9997 | william.chung@woods.co.nz |
| Peter Jane | WDHB Facilities Manager |  |  | 021 598 971 |  |
| Raymond Webb | MOE Regional Manager | Normanby Street | 09 632 9395 | 027 580 3071 | raymond.webb@minedu.govt.nz |
| Sandra Orr | MOE Team Leader Network | Normanby Street | 09 632 9373 |  | sandra.orr@minedu.govt.nz |
| Graeme Wilson | MOE ? |  | 09 632 9469 |  |  |
| Dr Sathananthan Kanagaratnam | Auckland Regional Dental Service - Clinical Director | WDHB | 09 838 1713 | 021 784 335 | sathananthan.kanagaratnam@waitematadbgbv.govt.nz |
| Elizabeth Schulze General Manager | SPARK Dental | 4 Tarndale Grove Albany | 09 414 3904 | 021 302 544 | elizabeth.schulze@spark-dental.com |
| Dr Carey Stevens | SPARK Dental Special Proj | 4 Tarndale Grove Albany | 09 415 1820 | 021 309 378 | carey.stevenson@spark-dental.com |
| RICHARD KNOWLES | Coffey Geotechical Silverdale | First Floor, 65-69 Forge Road Silverdale 0932 | (9) 426 9707 | 021 870 902 | Richard_Knowles@coffey.com |
| Grant Brown | MOE Network Facilitator | Level 3 Eden 5 Bldg Cnr Edwin St and Normanby Rd Mt Eden Auckland | 09 632 9384 | Fax 09 632 9401 | grant.brown@minedu.govt..nz |
| Andrew Stoakes Project Manager | healthAlliance Information Services |  | DDI: (09) 487 1519 Ex: 7519 | Mob: 021 784155 | andrew.stoakes@healthalliance.co.nz |
| Ken Merchant Security Design | Opus International Consultants | L3 The Westhaven, 100 Beaumont St PO Box 5848 Auckland | 09 355 9500 | 09 355 9583 027 294 0485 | Ken.Merchant@opus.co.nz |
| Jeremy Eggleton Security Partner | Opus International Consultants | L3 The Westhaven, 100 Beaumont St PO Box 5848 Auckland | 09 355 9500 09 355 9650 | 09 355 9583 021 630 303 | Jeremy.Eggleton@opus.co.nz |
| John Childs | Town Planner | 1/37 Lloyd Ave Mt Albert | 09 846 3152 | 09274 731 550 | John.Childs@xtra.co.nz |
| Thoma Cullum - | Dental Manager WDHB |  |  | 021 968 722 | Thoma.Cullum@waitematadhb.govt.nz |
| Heather Barnes - | Dental Manager WDHB |  |  | 021 968 415 | Heather.Barnes@waitematadhb.govt.nz |
| Dianne Houston - | Dental Manager WDHB |  |  | 021 968 975 | Dianne.Houston@waitematadhb.govt.nz |
| Carol Taylor - | Dental Manager WDHB |  |  | 021 968 401 | Carol.Taylor@waitematadhb.govt.nz |

I apologise for any errors in this schedule and ask that you contact me using the details below and update me with any corrections. Thank you.