## Edmonton Budget
Edmonton Primary School 2 Chair Clinic
ORACLE CODES | WDHB Oral | [5 empty] | Ex GST @ 12.5% |  |  |  |  | 1F | Fixed Facility
[5 empty] | Date This Report | 2010-08-01 | Actual Spend to Date |  |  |  |  | 2T | Transportable Unit
|  | Commitment Authorisation |  |  |  |  | May Payment |  | June Payment |  | Balance Remaining | 3S | Site Pad
| Allocation | Previous | Further | Total - Commitment | Element | Organisation | % Claimed | Invoice This Month | % Claimed | Invoice This Month |  | 4V | Driveables
1F0201A | ENABLING WORKS | 0 | 0 | 0 | Design |  | 0% | 0 | 0% | 0 | 0 | 5E | Fixtures Fittings and Equipment
| Opex Cost | 0 | 0 | 0 | Construction % Margin |  | 0% | 0 | 0% | 0 | 0 | A | Enabling Works
|  | 0 | 0 | 0 | Services HVAC E & F |  | 0% | 0 | 0% | 0 | 0 | B | Design Management
| ENABLING TOTAL | 0 | 0 | 0 |  |  | 0% | 0 | 0% | 0 | 0 | C | Construction and Fitout
1F0201B | DESIGNERS |  |  |  |  | ` | [5 empty] | D | Council Consents/Levies
|  | 28500 | 0 | 28500 | Architect | Kay and Keys | 41.98% | 11964.1 | 49% | 2000 | 14535.9 | E | Lease Legal
|  | 19830 | 0 | 19830 | Civil & Structural Engr | Woods | 48.62% | 9642 | 0% | 0 | 10188 | F | Contingency
|  | 6000 | 0 | 6000 | Services HVAC E & F | Aurecon | 136.5% | 8189 | 184% | 2851 | -5040 | G | Plant Fixed
|  | 4000 | 0 | 4000 | RMA Consultant | John Childs | 46.47% | 1858.72 | 0% | 0 | 2141.28 | H | Plant TDU
| Pro Rata | 6890 | 0 | 6890 | Traffic Engineer | Flow Tranportation | 62.79% | 4326 | 0% | 0 | 2564 | I | Plant Driveable
| Even Distribution | 14900 | 0 | 14900 | Quantity Surveyor | Rider Levelt Bucknall | 9.396% | 1400 | 0% | 0 | 13500 | J | Other
| DESIGNERS TOTAL | #VALUE! | #VALUE! | #VALUE! |  |  | #VALUE! | #VALUE! | 233% | #VALUE! | #VALUE! | V | Purchase
1F0201C | CONSTRUCTION AND FITOUT
|  | 32268 | 0 | 32268 | Preliminary & General | Gibson O'connor | 0% | 0 | 0% | 0 | 32268
|  | 48077 | 0 | 48077 | Excavation & Siteworks | Kidd | 0% | 0 | 0% | 0 | 48077
|  | 13437 | 0 | 13437 | Concrete Work & Additional Subfloor | Gibson O'connor | 0% | 0 | 0% | 0 | 13437
|  | 649 | 0 | 649 | Reinforcing Steel | Reofab | 0% | 0 | 0% | 0 | 649
|  | 5900 | 0 | 5900 | Structural Steel & Metalwork | Powerhouise | 0% | 0 | 0% | 0 | 5900
|  | 17471 | 0 | 17471 | Metal Windows Doors | Bradnams | 0% | 0 | 0% | 0 | 17471
|  | 107289 | 0 | 107289 | Carpentry | Gibson O'connor | 0% | 0 | 0% | 0 | 107289
|  | 23825 | 0 | 23825 | Joinery | The Cabibnet Place | 0% | 0 | 0% | 0 | 23825
|  | 10580 | 0 | 10580 | Metal Roofing | Hopkins | 0% | 0 | 0% | 0 | 10580
|  | 29350 | 0 | 29350 | Plumbing | Bassett | 0% | 0 | 0% | 0 | 29350
|  | 21500 | 0 | 21500 | Drainage | AFM | 0% | 0 | 0% | 0 | 21500
|  | 35287 | 0 | 35287 | Mechanical Services | Degree/Heron | 0% | 0 | 0% | 0 | 35287
|  | 31218 | 0 | 31218 | Electrical Services | Coast | 0% | 0 | 0% | 0 | 31218
|  | 10432 | 0 | 10432 | Plasterboard Linings | Troake | 0% | 0 | 0% | 0 | 10432
|  | 3950 | 0 | 3950 | Suspended Ceilings | Ace | 0% | 0 | 0% | 0 | 3950
|  | 10260 | 0 | 10260 | Floor Coverings | Comfloor | 0% | 0 | 0% | 0 | 10260
|  | 8475 | 0 | 8475 | Painting | Auckland Commercial | 0% | 0 | 0% | 0 | 8475
|  | 1935 | 0 | 1935 | Glazing | Veridian | 0% | 0 | 0% | 0 | 1935
|  | 20125 | 0 | 20125 | Sites Treated individually | Gibson O'connor | 0% | 0 | 0% | 0 | 20125
|  | 3605 | 0 | 3605 | APL Vantage Suite | Gibson O'connor | 0% | 0 | 0% | 0 | 3605
|  | 6557 | 0 | 6557 | Vector Charges | Gibson O'connor | 0% | 0 | 0% | 0 | 6557
|  | 7568 | 0 | 7568 | Illuminated Signage | Gibson O'connor | 0% | 0 | 0% | 0 | 7568
|  | 0 | 0 | 0 | Miscellaneous | TBA | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Contingency | None | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Prime Cost Sums | Refer tiling | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Provisional Sums | TBA | 0% | 0 | 0% | 0 | 0
| BUILDING TOTAL | #VALUE! | 0 | 449758 |  |  | 0% | 0 | 0 | 0 | 449758
1F0201D | Waitakere City Council | 2500 | 0 | 2500 | Outline Plan Works | Now Resource Consent | 0% | 807 | 0% | 631.05 | 1061.95
| Waitakere City Council | 7500 | 0 | 7500 | Council Fees | Building Consent | 0% | 541.564 | 0% | 5952.23 | 1006.206
| LAND TOTAL | 10000 | 0 | 10000 |  |  | 0% | 1348.564 | 0% | 6583.28 | 2068.156
1F0201F | Design Construction Contingency
| Design Contingency | 12318 | 0 | 12318 | Contingency |  | 0% | 0 | 0% | 0 | 12318
| Construction Contingency | 74242 |  |  | Construction % Margin | WDHB
| CONTINGENCY TOTAL | 96560 | 0 | 22318 |  |  | 0% | 1348.564 | 0% | 6583.28 | 14386.156
1F0201G | Plant Fixed
| Compressed air | 4428 | 0 | 4428 | Ivoclar vivadent Ltd but DHB order direct Cattanni | Cattani K200 x1 | 0% | 0 | 0% | 0 | 4428
| Suction/Amalgam Separator Turbosmart A | 8080 | 0 | 8080 | Cattani ISO 11143 Direct DHB to Ivoclar | ISO Amalgam Separator | 0% | 0 | 0% | 0 | 8080
[7 empty] | 0% | 0 | 0% | 0 | 0
| Washer plus installation | 0 | 0 | 0 | Steelco DS50DRSD Benchtop Plus includes the Installation | Mercer Medical Equipment - No washers for 2 and 3 chair | 0% | 0 | 0% | 0 | 0
| FIXED PLANT TOTAL | 8080 | 0 | 8080 |  |  | 0% | 0 | 0% | 0 | 8080
5E1F0201 | Client Fixtures Fittings Equipment | Clinic Closures - Henderson North; Summerland; Freyberg; Arahoe; Western Hts; Bruce McLaren; Henderson South; Henderson School; Peninsula; Pomaria; Rutherford; Te Atatu Int; Birwood; Doln Buck; Massey;\ Ranui;
| Dental Chairs Existing | 0 | 0 | 0 | 2x New Adec 500 Chairs |  | 0% | 0 | 0% | 0 | 0
| Operating light | 0 | 0 | 0 | 2X ADEC Chair or ceiling mountedLights |  | 0% | 0 | 0% | 0 | 0
| Dental Chairs New Adec 500 Chair (Plus assistant stool minus assistant arm) | 38520 | 0 | 38520 | Adec 500 chair /light (minus assistant stool minus assistance arm) | Ivoclar vivadent Ltd | 0% | 0 | 0% | 0 | 38520
| Dental Carts/Units | 0 | 0 | 0 | Resuse existing Carts; Post Drill to Ensure Chairs and Carts services come up at foot of chairs. |  | 0% | 0 | 0% | 0 | 0
| Autoclave (statim) | 0 | 0 | 0 | ( 1x Staim s 2000 Edmonton Remains) |  | 0% | 0 | 0% | 0 | 0
| Lisa (B Class) | 0 |  |  | NA to 2 Chair |  | 0% | 0 | 0% | 0 | 0
| Xray Machine | 0 | 0 | 0 | 1x Ardet Pamotine (Edmonton, remain) |  | 0% | 0 | 0% | 0 | 0
| Xray developer | 0 | 0 | 0 | 1x Durr Periomat (Edmonton, remains) |  | 0% | 0 | 0% | 0 | 0
| Curing Light | 0 | 0 | 0 | 2x SDI LED Cordless Curing Light Edmonton remains) |  | 0% | 0 | 0% | 0 | 0
| Amalgamator Existing | 0 | 0 | 0 | NA |  | 0% | 0 | 0% | 0 | 0
| Amalgamator New | 1530 | 0 | 1530 | Satelec FO3160 | Gunz dental | 0% | 0 | 0% | 0 | 1530
| Water Filter Demonizing Unit | 890 | 0 | 890 | Was 1xspringflow, Northcote Int but it now Ivoclar vivadent 297563 Lise Dem 32 Demonizing unit |  | 0% | 0 | 0% | 0 | 890
| Water Filter Cartridge | 420 | 0 | 420 | Was 1xspringflow, Northcote Int but now Ivoclar vivadent 297563 Lise Dem 32 Resin cartiridge Pkt 4 |  | 0% | 0 | 0% | 0 | 420
| Oiling Unit for Hand Pieces | 0 | 0 | 0 | NSK N/A until using NSK handpieces | No Oiling - Belinda to Add Kavo Later | 0% | 0 | 0% | 0 | 0
| Filling trays , Preventive trays, Examination trays (awaiting quote) HCE | 1967.04 | 0 | 1967.04 | 16 x 10 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1967.04
|  | 3053.76 | 0 | 3053.76 | 24x7 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 3053.76
|  | 1622.08 | 0 | 1622.08 | 16x 5 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1622.08
|  | 900 | 0 | 900 | Carparking/Yard |  | 0% | 0 | 0% | 0 | 900
|  | 900 | 0 | 900 | Freight & installation |  | 0% | 0 | 0% | 0 | 900
| 12 Oclocks | 18322 | 0 | 18322 | Ordered incl Freight | Units from DentalEZ | 0% | 0 | 0% | 0 | 18322
Miscellaneouls
Danbar Chairs
| CLIENT FITOUT TOTAL | 80632.88 | 0 | 80632.88 | Fitout Sub Total |  | 0 | 0 | 0 | 0 | 80632.88
P1F0201 | General Contingency | 40000 | 0 | 40000 | Contingency |  | 0% | 0 | 0% | 0 | 40000
| CONTINGENCY TOTAL | 80632.88 | 0 | 80632.88 | Fitout Sub Total |  | 0 | 0 | 0 | 0 | 80632.88
Tray Contents (Distribute Qty Evenly)
| Mirror | x5
| Probe | x5
| Triple syringe nozzle | x5 |  | Edmonton | Yes | Wilsonart 7219-58 Forest Terra | Chrystal Mint
| 2 tweezers | x10 |  | Edmonton | Yes | Wilsonart 7900-60 Fusion Maple | Calypso Melange
| Excavators (3 sizes) | x15
| Amalgam plugger | x5
| Plastic | x5
| Cement plugger | x5
| Dycal instrument | x5
| Oscoid discoid | x5
| Ball burnisher | x5
| Wax carver | x5
Additional requirements
| Syringes x 6 | x6
| Needle guards x 6 | x6
| Rubber dam frames x 2 | x2
| Cotton roll holders (pair) | x2
| Clamps x 2 | x2
| Matrix band (s) x 6 of each | 1x6
| Applicators x 5 | x5
| Preventive trays (Distribute Qty Evenly) | x3
| Mirror | x3
| Probe | x3
| Triple syringe nozzle | x3
| 2 tweezers | x6
| Ball burnisher | x3
| Dycal instrument | x3
Additional requirements
| Rubber dam | x1
| Clamps | x3
| Cotton roll holders | x3
| Examination for 2x Trays (Distribute Qtys Evenly) | x2
| 20 mirrors | x40
| 20 probes | x40
| 10 triple syringes | x20
| 10 tweezers | x20
Additional requirements
Nil
Bags
Forceps
| 1 Set per FDU | x1
Excavators
| 1 Set per FDU | x1
Totals

## Glenfield Budget
Glenfield Intermediate School 4 Chair Clinic
ORACLE CODES | WDHB Oral | [5 empty] | Ex GST @ 12.5%
[5 empty] | Date This Report | 2010-08-01 | Actual Spend to Date
|  | Commitment Authorisation |  |  |  |  | May Payment |  | June Payment |  | Balance Remaining
| Allocation | Previous | Further | Total - Commitment | Element | Organisation | % Claimed | Invoice This Month | % Claimed | Invoice This Month
| LAND | 0 | 0 | 0 | Purchase |  | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Legals |  | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Enabling Works |  | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Other |  | 0% | 0 | 0% | 0 | 0
| LAND TOTAL | 0 | 0 | 0 |  |  | 0% | 0 | 0% | 0 | 0
| DEVELOPMENT | 0 | 0 | 0 | WDHB Facilities |  | 0% | 0 | 0% | 0 | 0
| Opex Cost | 0 | 0 | 0 | WDHB Expences |  | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | HA Specialists |  | 0% | 0 | 0% | 0 | 0
| DEVELOPMENT TOTAL | 0 | 0 | 0 |  |  | 0% | 0 | 0% | 0 | 0
| DESIGNERS |  |  |  |  | `
|  | 33500 | 0 | 33500 | Architect | Kay and Keys | 44.57% | 14929.6 | 47.55% | 1000 | 17570.4
|  | 19960 | 0 | 19960 | Civil & Structural Engr | Woods | 49.95% | 9970 | 0% | 0 | 9990
|  | 7000 | 0 | 7000 | Services HVAC E & F | Aurecon | 136.5% | 9554 | 184% | 3326 | -5880
|  | 4000 | 0 | 4000 | RMA Consultant | John Childs | 22.47% | 898.72 | 0% | 0 | 3101.28
| Pro Rata | 8268 | 0 | 8268 | Traffic Engineer | Flow Tranportation | 62.79% | 5191.67 | 0% | 0 | 3076.33
| Even Distribution | 14900 | 0 | 14900 | Quantity Surveyor | Rider Levelt Bucknall | 9.396% | 1400 | 0% | 0 | 13500
|  | 12318 | 0 | 12318 | Contingency |  | 0% | 0 | 0% | 0 | 12318
| DESIGNERS TOTAL | 99946 | 0 | 99946 |  |  | 46.52% | 41943.99 | 33.08% | 4326 | 53676.01
SPECIALISTS
|  | 4500 | 0 | 4500 | Surveyor | Wood & Ptnrs | 49.76% | 2239 | 0% | 0 | 2261
|  | 4500 | 0 | 4500 | Geotech. Engr | Coffey Geotechnical | 38.67% | 1740 | 0% | 0 | 2760
|  | 1000 | 0 | 1000 | Contingency |  | 0% | 0 | 0% | 0 | 1000
[5 empty] | Design % Margin | WDHB
| SPECIALISTS TOTAL | 10000 | 0 | 10000 |  |  | 29.47% | 3979 | 0% | 0 | 6021
NON CLINICAL
| BUILDING | 38033 | 0 | 38033 | Preliminary & General | Gibson O'connor | 0% | 0 | 0% | 0 | 38033
| 640000 | 59025 | 0 | 59025 | Excavation & Siteworks | Kidd | 0% | 0 | 0% | 0 | 59025
|  | 20204 | 0 | 20204 | Concrete Work & Additional Subfloor | Gibson O'connor | 0% | 0 | 0% | 0 | 20204
|  | 708 | 0 | 708 | Reinforcing Steel | Reofab | 0% | 0 | 0% | 0 | 708
|  | 5900 | 0 | 5900 | Structural Steel & Metalwork | Powerhouise | 0% | 0 | 0% | 0 | 5900
|  | 23113 | 0 | 23113 | Metal Windows Doors | Bradnams | 0% | 0 | 0% | 0 | 23113
|  | 155099 | 0 | 155099 | Carpentry | Gibson O'connor | 0% | 0 | 0% | 0 | 155099
|  | 29103 | 0 | 29103 | Joinery | The Cabibnet Place | 0% | 0 | 0% | 0 | 29103
|  | 14480 | 0 | 14480 | Metal Roofing | Hopkins | 0% | 0 | 0% | 0 | 14480
|  | 43335 | 0 | 43335 | Plumbing | Bassett | 0% | 0 | 0% | 0 | 43335
|  | 16750 | 0 | 16750 | Drainage | AFM | 0% | 0 | 0% | 0 | 16750
|  | 42267 | 0 | 42267 | Mechanical Services | Degree/Heron | 0% | 0 | 0% | 0 | 42267
|  | 57203 | 0 | 57203 | Electrical Services | Coast | 0% | 0 | 0% | 0 | 57203
|  | 15701 | 0 | 15701 | Plasterboard Linings | Troake | 0% | 0 | 0% | 0 | 15701
|  | 6460 | 0 | 6460 | Suspended Ceilings | Ace | 0% | 0 | 0% | 0 | 6460
|  | 16732 | 0 | 16732 | Floor Coverings | Comfloor | 0% | 0 | 0% | 0 | 16732
|  | 12890 | 0 | 12890 | Painting | Auckland Commercial | 0% | 0 | 0% | 0 | 12890
|  | 1935 | 0 | 1935 | Glazing | Veridian | 0% | 0 | 0% | 0 | 1935
|  | 24475 | 0 | 24475 | Sites Treated individually | Gibson O'connor | 0% | 0 | 0% | 0 | 24475
|  | 3767 | 0 | 3767 | APL Vantage Suite | Gibson O'connor | 0% | 0 | 0% | 0 | 3767
|  | 9706 | 0 | 9706 | Vector Charges | Gibson O'connor | 0% | 0 | 0% | 0 | 9706
|  | 7568 | 0 | 7568 | Illuminated Signage | Gibson O'connor | 0% | 0 | 0% | 0 | 7568
|  | 0 | 0 | 0 | Miscellaneous | TBA | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Contingency | None | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Prime Cost Sums | Refer tiling | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Provisional Sums | TBA | 0% | 0 | 0% | 0 | 0
|  | 117000 | 0 | 117000 | Constrcution % Margin | WDHB
| BUILDING TOTAL | 721454 | 0 | 721454 |  |  | 0% | 0 | 0 | 0 | 604454
| CLINICAL | Clinics - Bayview; Manukau; Beachhaven; Birkdale Intermediate; Birkdale North; Northcotes Intermediate; Target Road; Northcote School;Willow Park;
BUILDING
| Dental Chairs Existing | 0 | 0 | 0 | 2X Royal GP11's (Target Rd); 2x Royals (Willow Park) |  | 0% | 0 | 0% | 0 | 0
| Operating light | 0 | 0 | 0 | (2x Faro s 2000, NSH 51878A, no number, Rutherford prim, 2xFaro s 2000, Glendene) |  | 0% | 0 | 0% | 0 | 0
| Dental Chairs New Adec 500 Chair (Plus assistant stool minus assistant arm) | 0 | 0 | 0 | Resused |  | 0% | 0 | 0% | 0 | 0
| Dental Carts/Units | 0 | 0 | 0 | ( 2x DCI DM4 Carts, WHL06085, WHA210020, Western Heights, 1x DM4 WHSA200477 Beachhaven, 1x DCI DM4, Arahoe) |  | 0% | 0 | 0% | 0 | 0
| Autoclave (statim) | 0 | 0 | 0 | (1X Statim, S2000 Arahoe, 1x Statim S2000, Bruce McLaren) |  | 0% | 0 | 0% | 0 | 0
| Lisa (B Class) | 0 | 0 | 0 | W&H Lisa517 | Ivoclar vivadent Ltd | 0% | 0 | 0% | 0 | 0
| Xray Machine | 0 | 0 | 0 | x1 Kodak 2200, Henderson North |  | 0% | 0 | 0% | 0 | 0
| Xray developer | 0 | 0 | 0 | x1 Durr Periomat, henderson North |  | 0% | 0 | 0% | 0 | 0
| Curing Light | 0 | 0 | 0 | x3 Demi Curing Light (Already Purchasedd) |  | 0% | 0 | 0% | 0 | 0
| Amalgamator | 0 | 0 | 0 | FO3160 (Already Purchased) |  | 0% | 0 | 0% | 0 | 0
| Water Filter Demonizing Unit | 890 | 0 | 890 | Was already ordered but it now Ivoclar vivadent 297563 Lise Dem 32 Demonizing unit |  | 0% | 0 | 0% | 0 | 890
| Water Filter Cartridge | 420 | 0 | 420 | Was already ordered but now Ivoclar vivadent 297563 Lise Dem 32 Resin cartiridge Pkt 4 |  | 0% | 0 | 0% | 0 | 420
| Compressed air | 5325 | 0 | 5325 |  | Cattani K300 x1 | 0% | 0 | 0% | 0 | 5325
| Suction/Amalgam Separator Turbosmart B | 9815 | 0 | 9815 | Cattani ISO 11143 Direct DHB to Ivoclar | ISO Amalgam Separator x1 off | 0% | 0 | 0% | 0 | 9815
| Washer | 9219 | 0 | 9219 | Steelco DS50DRSD Benchtop Plus includes the Installation | Mercer Medical Equipment | 0% | 0 | 0% | 0 | 9219
| Oiling Unit for Hand Pieces -To Go Under Bench in the Reprocessing Room | 5000 | 0 | 5000 | NSK N/A until using NSK handpieces | Oiling Unit Required - Dentalectra to Quote | 0% | 0 | 0% | 0 | 5000
| Filling trays , Preventive trays, Examination trays (awaiting quote) HCE | 1475.28 | 0 | 1475.28 | 12 x 10 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1475.28
|  | 2290.32 | 0 | 2290.32 | 18x7 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 2290.32
|  | 1216.56 | 0 | 1216.56 | 12x 5 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1216.56
|  | 900 | 0 | 900 | Carparking/Yard |  | 0% | 0 | 0% | 0 | 900
|  | 900 | 0 | 900 | Freight & installation |  | 0% | 0 | 0% | 0 | 900
|  | 36644 | 0 | 36644 | 12 Oclock | Units from DentalEZ | 0% | 0 | 0% | 0 | 36644
Miscellaneouls
Danbar Chairs
| FITOUT TOTAL | 74095.16 | 0 | 74095.16 | Fitout Sub Total |  | 0 | 0 | 0 | 0 | 74095.16
| Early Costs | 0 | 0 |  |  |  | 0% | 0 | 0 | 0 | 0
| North Shore Cityh Council | 2500 | 0 | 2500 | Outline Plan Works | Outline Plan Consent | 0% | 1000 | 0% | 1075.79 | 424.21
| North Shore City Council | 7500 | 0 | 7500 | Council Fees | Building Consent | 0% | 6800.1 | 0% | 0 | 699.9
|  | 0 | 0 | 0 | Contractor Margin |  | 0% | 0 | 0% | 0 | 0
|  | 40000 | 0 | 40000 | Contingency |  | 0% | 0 | 0% | 0 | 40000
| TOTAL | 955495.16 | 0 | 955495.16 |  |  |  | 53723.09 | 0.33079 | 5401.79 | 779370.28
Allowed for as Building Plant
Note 1: Claims by contractors may be by percentages but claims by Consultants may be in Actual costs
Tray Contents (Distribute Qty Evenly)
| Mirror | x6
| Probe | x6 |  |  | Glenfield | Yes | Wilsonart 4651-60 Navy Legacy | Chrystal Blue
| Triple syringe nozzle | x6 |  |  | Glenfield | Yes | Wilsonart 7900-60 Fusion Maple | Calypso Melange
| 2 tweezers | x12 |  |  | Glenfield | Yes | Wilsonart 7900-60 Fusion Maple | Calypso Melange
| Excavators (3 sizes) | x18 |  |  | Glenfield | Yes | Wilsonart 7219-58 Forest Terra | Chrystal Mint
| Amalgam plugger | x6
| Plastic | x6
| Cement plugger | x6
| Dycal instrument | x6
| Oscoid discoid | x6
| Ball burnisher | x6
| Wax carver | x6
Additional requirements
| Syringes x 6 | x6
| Needle guards x 6 | x6
| Rubber dam frames x 2 | x2
| Cotton roll holders (pair) | x2
| Clamps x 2 | x2
| Matrix band (s) x 6 of each | 1x6
| Applicators x 5 | x5
| Preventive trays (Distribute Qty Evenly) | x5
| Mirror | x5
| Probe | x5
| Triple syringe nozzle | x5
| 2 tweezers | x10
| Ball burnisher | x5
| Dycal instrument | x5
Additional requirements
| Rubber dam | x1
| Clamps | x3
| Cotton roll holders | x3
| Examination for 2x Trays (Distribute Qtys Evenly) | x3
| 20 mirrors | x60
| 20 probes | x60
| 10 triple syringes | x30
| 10 tweezers | x30
Additional requirements
Nil
Bags
Forceps
| 1 Set per FDU | x1
Excavators
| 1 Set per FDU | x1
Fat Client PC -
Local Image Capture Software - (Titanium Stand Alone)
Totals

## Henderson Budget
Henderson Intermediate School 6 Chair Clinic
ORACLE CODES | WDHB Oral | [5 empty] | 0
[5 empty] | Date This Report | 2010-08-01 | Actual Spend to Date
|  | Commitment Authorisation |  |  |  |  | May Payment |  | June Payment |  | July Payment |  | Balance Remaining
| Allocation | Previous | Further | Total - Commitment | Element | Organisation | % Claimed | Invoice This Month | % Claimed | Invoice This Month | % Claimed | Invoice This Month
| LAND | 0 | 0 | 0 | Purchase |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Legals |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Enabling Works |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Other |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
| LAND TOTAL | 0 | 0 | 0 |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
| DEVELOPMENT | 0 | 0 | 0 | WDHB Facilities |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
| Opex Cost | 0 | 0 | 0 | WDHB Expences |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | HA Specialists |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
| DEVELOPMENT TOTAL | 0 | 0 | 0 |  |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
DESIGNERS
|  | 35500 | 0 | 35500 | Architect | Kay and Keys | 44.27% | 15714.4 | 51.94% | 2723.36 | #VALUE! | 2723.36 | 17062.24
|  | 26950 | 0 | 26950 | Civil & Structural Engr | Woods | 52.38% | 14116 | 0% | 0 | 0% | 0 | 12834
|  | 8000 | 0 | 8000 | Services HVAC E & F | Aurecon | 136.5% | 10919 | 184% | 3801 | #VALUE! | 3801 | -6720
|  | 4000 | 0 | 4000 | RMA Consultant | John Childs | 46.47% | 1858.72 | 0% | 0 | 0% | 0 | 2141.28
| Pro Rata | 9646 | 0 | 9646 | Traffic Engineer | Flow Tranportation | 62.8% | 6057.33 | 0% | 0 | 0% | 0 | 3588.67
| Even Distribution | 14900 | 0 | 14900 | Quantity Surveyor | Rider Levelt Bucknall | 9.396% | 1400 | 0% | 0 | 0% | 0 | 13500
|  | 12318 | 0 | 12318 | Contingency |  | 0% | 0 | 0% | 0 | 0% | 0 | 12318
| DESIGNERS TOTAL | 111314 | 0 | 111314 |  |  | 50.26% | 50065.45 | 33.71% | 6524.36 | #VALUE! | 6524.36 | 54724.19
SPECIALISTS
|  | 4500 | 0 | 4500 | Surveyor | Wood & Ptnrs | 50.08% | 2253.6 | 0% | 0 | 0% | 0 | 2246.4
|  | 4500 | 0 | 4500 | Geotech. Engr | Coffey Geotechnical | 34.44% | 1550 | 104.4% | 3145.77 | #VALUE! | 3145.77 | -195.77
|  | 1000 | 0 | 1000 | Contingency |  | 100% | 1000 | 0% | 0 | 0% | 0 | 0
| SPECIALISTS TOTAL | 10000 | 0 | 10000 |  |  | 61.51% | 4803.6 | 34.78% | 3145.77 | #VALUE! | 3145.77 | 2050.63
NON CLINICAL
| BUILDING | 40837 | 0 | 40837 | Preliminary & General | Gibson O'connor | 0% | 0 | 0% | 0 | 0% | #VALUE! | 40837
| 640000 | 67557 | 0 | 67557 | Excavation & Siteworks | Kidd | 0% | 0 | 0% | 0 | 0% | #VALUE! | 67557
|  | 37156 | 0 | 37156 | Concrete Work & Additional Subfloor | Gibson O'connor | 0% | 0 | 0% | 0 | 0% | #VALUE! | 37156
|  | 725 | 0 | 725 | Reinforcing Steel | Reofab | 0% | 0 | 0% | 0 | 0% | #VALUE! | 725
|  | 6330 | 0 | 6330 | Structural Steel & Metalwork | Powerhouise | 0% | 0 | 0% | 0 | 0% | #VALUE! | 6330
|  | 28564 | 0 | 28564 | Metal Windows Doors | Bradnams | 0% | 0 | 0% | 0 | 0% | #VALUE! | 28564
|  | 179716 | 0 | 179716 | Carpentry | Gibson O'connor | 0% | 0 | 0% | 0 | 0% | #VALUE! | 179716
|  | 29319 | 0 | 29319 | Joinery | The Cabinet Place | 0% | 0 | 0% | 0 | 0% | #VALUE! | 29319
|  | 18560 | 0 | 18560 | Metal Roofing | Hopkins | 0% | 0 | 0% | 0 | 0% | #VALUE! | 18560
|  | 54923 | 0 | 54923 | Plumbing | Bassett | 0% | 0 | 0% | 0 | 0% | #VALUE! | 54923
|  | 36250 | 0 | 36250 | Drainage | AFM | 0% | 0 | 0% | 0 | 0% | #VALUE! | 36250
|  | 51888 | 0 | 51888 | Mechanical Services | Degree/Heron | 0% | 0 | 0% | 0 | 0% | #VALUE! | 51888
|  | 61972 | 0 | 61972 | Electrical Services | Coast | 0% | 0 | 0% | 0 | 0% | #VALUE! | 61972
|  | 18566 | 0 | 18566 | Plasterboard Linings | Troake | 0% | 0 | 0% | 0 | 0% | #VALUE! | 18566
|  | 8050 | 0 | 8050 | Suspended Ceilings | Ace | 0% | 0 | 0% | 0 | 0% | #VALUE! | 8050
|  | 20450 | 0 | 20450 | Floor Coverings | Comfloor | 0% | 0 | 0% | 0 | 0% | #VALUE! | 20450
|  | 13895 | 0 | 13895 | Painting | Auckland Commercial | 0% | 0 | 0% | 0 | 0% | #VALUE! | 13895
|  | 1830 | 0 | 1830 | Glazing | Veridian | 0% | 0 | 0% | 0 | 0% | #VALUE! | 1830
|  | 0 | 0 | 0 | Sites Treated individually | Gibson O'connor
|  | 3031 | 0 | 3031 | APL Vantage Suite | Gibson O'connor
|  | 23739 | 0 | 23739 | Vector Prov Sum | Gibson O'connor
|  | 7568 | 0 | 7568 | Illuminated Signage | Gibson O'connor
|  | 0 | 0 | 0 | Miscellaneous |  | 0% | 0 | 0% | 0 | 0% | 0 | 0
|  | 0 | 0 | 0 | Contingency | None | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
|  | 0 | 0 | 0 | Prime Cost Sums | Refer tiling | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
|  | 0 | 0 | 0 | Provisional Sums | Vector | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
|  | 142261 | 0 | 142261 | Construction % Margin | WDH B
| BUILDING TOTAL | 853187 | 0 | 853187 |  |  | 0% | 0 | 0 | 0 | 0 | #VALUE! | 676588
RELOCATE CLASSROOMS
| Design | 0 | 0 | 0 | Design | Waitakere Architects | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
| Geotech | 0 | 0 | 0 | Geotech | Coffey Geotech | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
| Contamineation | 0 | 0 | 0 | Contamination | Coffey Geotech | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
| Outline Plan | 0 | 0 | 0 | Outline Plan | Waitakere Architects | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
| Waitakere OPW | 0 | 0 | 0 | Waitakere OPW | Waitakere City Council | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
| Waitakere Bldg Cnsent | 0 | 0 | 0 | Waitakere Bldg Cnsent | Waitakere City Council | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
| Construction A | 0 | 0 | 0 | Construction A | Stonebridge | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
| Construction B | 0 | 0 | 0 | Construction B | Gibson Oconnor | 0% | 0 | 0% | 0 | 0% | #VALUE! | 0
| CLINICAL | Clinic Closures - Henderson North; Summerland; Freyberg; Arahoe; Western Hts; Bruce McLaren; Henderson South; Henderson Intermediate; Peninsula; Pomaria; Rutherford; Te Atatu Int; Birwood; Doln Buck; Massey;\ Ranui;
BUILDING
| Dental Chairs Existing | 0 | 0 | 0 | 3x Royals (Origins TBC), 3x Belmonts for AUT (Northcote intermediate); |  | 0% | 0 | 0% | 0 |  |  | 0
| Operating light | 2890 | 0 | 2890 | (3X AEDC Chair or ceiling mounted) (1x Faro S 2000 WHL02414 Western heights, 1X FARO s2000 nsh 51839a Freyburg, 1Xfaro EDI Te Atatu Int , WHL02719) |  | 0% | 0 | 0% | 0 |  |  | 2890
| Dental Chairs New Adec 500 Chair (Plus assistant stool minus assistant arm) | 22150 | 0 | 22150 | Adec 500 chair /light (Plus assistant stool minus assistant arm) | Ivoclar vivadent Ltd | 0% | 0 | 0% | 0 |  |  | 22150
| Dental Carts/Units | 4250 | 0 | 4250 | 2xDCI DM4 (Edmonton) 1X new Forest cart 5200 NHSS (3 ADEC radius see below) |  | 0% | 0 | 0% | 0 |  |  | 4250
| Autoclave (statim) | 0 | 0 | 0 | ( 1x Staim s 2000 Henderson Int remains 1x Statim S 2000 Arahoe) |  | 0% | 0 | 0% | 0 |  |  | 0
| Lisa (B Class) | 10200 |  | 10200 | W&H Lisa517 | Ivoclar vivadent Ltd | 0% | 0 | 0% | 0 |  |  | 10200
| Xray Machine | 5585 | 0 | 5585 | 2x Plan Meca Henderson Int (Both Wall Mounted) |  | 0% | 0 | 0% | 0 |  |  | 5585
| Xray developer | 0 | 0 | 0 | 1x Durr Periomat Plus Henderson Int 1 x Only |  | 0% | 0 | 0% | 0 |  |  | 0
| Curing Light | 0 | 0 | 0 | (1xSDI Radii plus Henderson Int) ( 2xESPE highlights and 1 xESPE Elipair 11 Northcote Int ) (1xESPE Elipair 11, 1x SDI Radii Plus cordlessLED Henderson North Primary) |  | 0% | 0 | 0% | 0 |  |  | 0
| Amalgamator Existing | 0 | 0 | 0 | (1x SDI ultramat 2, Bruce Mc Laren ) (1xSDI ultramat 2, 1X Satelic Softly Northcote Int) |  | 0% | 0 | 0% | 0 |  |  | 0
| Amalgamator New | 654 | 0 | 654 | Satelec FO3160 | Gunz dental | 0% | 0 | 0% | 0 |  |  | 654
| Water Filter Demonizing Unit | 890 | 0 | 890 | Was 1xspringflow, Northcote Int but it now Ivoclar vivadent 297563 Lise Dem 32 Demonizing unit |  | 0% | 0 | 0% | 0 |  |  | 890
| Water Filter Cartridge | 420 | 0 | 420 | Was 1xspringflow, Northcote Int but now Ivoclar vivadent 297563 Lise Dem 32 Resin cartiridge Pkt 4 |  | 0% | 0 | 0% | 0 |  |  | 420
| Compressed air | 10702 | 0 | 10702 | Ivoclar vivadent Ltd but DHB direct to Cattani | Cattani K300 x2 | 0% | 0 | 0% | 0 |  |  | 10702
| Suction/Amalgam Margin .08% Separator Turbosmart A | 16160 | 0 | 16160 | Cattani ISO 11143 Direct DHB via Ivoclar | ISO Amalgam Separators x2 | 0% | 0 | 0% | 0 |  |  | 16160
| Washer | 9219 | 0 | 9219 | Steelco DS50DRSD Benchtop Plus includes the Installation | Mercer Medical Equipment | 0% | 0 | 0% | 0 |  |  | 9219
| Oiling Unit for Hand Pieces | 0 | 0 | 0 | NSK N/A until using NSK handpieces | No Oiling - Belinda to Add Kavo Later | 0% | 0 | 0% | 0 |  |  | 0
| Filling trays , Preventive trays, Examination trays (awaiting quote) HCE | 1475.28 | 0 | 1475.28 | 12 x 10 set | Hu Freidy Quote | 0% | 0 | 0% | 0 |  |  | 1475.28
|  | 2290.32 | 0 | 2290.32 | 18x7 set | Hu Freidy Quote | 0% | 0 | 0% | 0 |  |  | 2290.32
|  | 1216.56 | 0 | 1216.56 | 12x 5 set | Hu Freidy Quote | 0% | 0 | 0% | 0 |  |  | 1216.56
|  | 900 | 0 | 900 | Carparking/Yard |  | 0% | 0 | 0% | 0 |  |  | 900
|  | 900 | 0 | 900 | Freight & installation |  | 0% | 0 | 0% | 0 |  |  | 900
|  | 54846 | 0 | 54846 | 12 Oclock | Units from DentalEZ | 0% | 0 | 0% | 0 |  |  | 54846
Miscellaneouls
Danbar Chairs
| FITOUT TOTAL | 144748.16 | 0 | 144748.16 | Fitout Sub Total |  | 0 | 0 | 0 | 0 |  |  | 144748.16
| Early Costs | 0 | 0 |  |  |  | 0% | 0 | 0 | 0 |  |  | 0
Provisional Sum 1
Provisional Sum 2
Provisional Sum 3
| Local Authority per Site | 5454 | 0 | 5454 | Council Fees | Waitakere City Council | 29.91% | 1631.53 | 41.48% | 631.05 |  |  | 3191.42
|  | 8000 | 0 | 8000 | Contractor Margin |  | 0% | 0 | 0 | 0 |  |  | 8000
|  | 40000 | 0 | 40000 | Contingency |  | 0% | 0 | 0 | 0 |  |  | 40000
| TOTAL | 1027955 | 0 | 1027955 |  |  |  | 56500.58 |  | 10301.18 |  |  | 784554.24
Allowed for as Building Plant
Note 1: Claims by contractors may be by percentages but claims by Consultants may be in Actual costs
Tray Contents (Distribute Qty Evenly)
| Mirror | x6
| Probe | x6 |  |  | Henderson | Yes | Wilsonart 4651-60 Navy Legacy | Chrystal Blue
| Triple syringe nozzle | x6 |  |  | Henderson | Yes | Wilsonart 4651-60 Navy Legacy | Chrystal Blue
| 2 tweezers | x12 |  |  | Henderson | Yes | Wilsonart 7900-60 Fusion Maple | Calypso Melange
| Excavators (3 sizes) | x18 |  |  | Henderson | Yes | Wilsonart 7900-60 Fusion Maple | Calypso Melange
| Amalgam plugger | x6 |  |  | Henderson | Yes | Wilsonart 7219-58 Forest Terra | Chrystal Mint
| Plastic | x6 |  |  | Henderson | Yes | Wilsonart 7219-58 Forest Terra | Chrystal Mint
| Cement plugger | x6
| Dycal instrument | x6
| Oscoid discoid | x6
| Ball burnisher | x6
| Wax carver | x6
Additional requirements
| Syringes x 6 | x6
| Needle guards x 6 | x6
| Rubber dam frames x 2 | x2
| Cotton roll holders (pair) | x2
| Clamps x 2 | x2
| Matrix band (s) x 6 of each | 1x6
| Applicators x 5 | x5
| Preventive trays (Distribute Qty Evenly) | x5
| Mirror | x5
| Probe | x5
| Triple syringe nozzle | x5
| 2 tweezers | x10
| Ball burnisher | x5
| Dycal instrument | x5
Additional requirements
| Rubber dam | x1
| Clamps | x3
| Cotton roll holders | x3
| Examination for 2x Trays (Distribute Qtys Evenly) | x3
| 20 mirrors | x60
| 20 probes | x60
| 10 triple syringes | x30
| 10 tweezers | x30
Additional requirements
Nil
Bags
Forceps
| 1 Set per FDU | x1
Excavators
| 1 Set per FDU | x1
Fat Client PC -
Local Image Capture Software - (Titanium Stand Alone)
Totals

## Equipment HendGlenEd
Henderson Intermediate School 6 Chair Clinic
WDHB Oral | [5 empty] | Ex GST @ 12.5%
|  |  |  | Date This Report | 2010-07-01 | Actual Spend to Date
CLINICAL | Clinic Closures - Henderson North; Summerland; Freyberg; Arahoe; Western Hts; Bruce McLaren; Henderson South; Henderson Intermediate; Peninsula; Pomaria; Rutherford; Te Atatu Int; Birwood; Doln Buck; Massey;\ Ranui;
BUILDING
Dental Chairs Existing | 0 | 0 | 0 | 3x Royals (Origins TBC), 3x Belmonts for AUT (Northcote intermediate); |  | 0% | 0 | 0% | 0 | 0
Operating light | 2890 | 0 | 2890 | (3X AEDC Chair or ceiling mounted) (1x Faro S 2000 WHL02414 Western heights, 1X FARO s2000 nsh 51839a Freyburg, 1Xfaro EDI Te Atatu Int , WHL02719) |  | 0% | 0 | 0% | 0 | 2890
Dental Chairs New Adec 500 Chair (Plus assistant stool minus assistant arm) | 22150 | 0 | 22150 | Adec 500 chair /light (Plus assistant stool minus assistant arm) | Ivoclar vivadent Ltd | 0% | 0 | 0% | 0 | 22150 | (1X Royal GP11 WHL02719, Te Atatu Int)
Dental Carts/Units | 4250 | 0 | 4250 | 2xDCI DM4 (Edmonton) 1X new Forest cart 5200 NHSS (3 ADEC radius see below) |  | 0% | 0 | 0% | 0 | 4250
Autoclave (statim) | 0 | 0 | 0 | ( 1x Staim s 2000 Henderson Int remains 1x Statim S 2000 Arahoe) |  | 0% | 0 | 0% | 0 | 0
Lisa (B Class) | 10200 |  | 10200 | W&H Lisa517 | Ivoclar vivadent Ltd | 0% | 0 | 0% | 0 | 10200
Xray Machine | 5585 | 0 | 5585 | 2x Plan Meca Henderson Int (Both Wall Mounted) |  | 0% | 0 | 0% | 0 | 5585
Xray developer | 0 | 0 | 0 | 1x Durr Periomat Plus Henderson Int 1 x Only |  | 0% | 0 | 0% | 0 | 0
Curing Light | 0 | 0 | 0 | (1xSDI Radii plus Henderson Int) ( 2xESPE highlights and 1 xESPE Elipair 11 Northcote Int ) (1xESPE Elipair 11, 1x SDI Radii Plus cordlessLED Henderson North Primary) |  | 0% | 0 | 0% | 0 | 0
Amalgamator Existing | 0 | 0 | 0 | (1x SDI ultramat 2, Bruce Mc Laren ) (1xSDI ultramat 2, 1X Satelic Softly Northcote Int) |  | 0% | 0 | 0% | 0 | 0
Amalgamator New | 654 | 0 | 654 | Satelec FO3160 | Gunz dental | 0% | 0 | 0% | 0 | 654
Water Filter Demonizing Unit | 890 | 0 | 890 | Was 1xspringflow, Northcote Int but it now Ivoclar vivadent 297563 Lise Dem 32 Demonizing unit |  | 0% | 0 | 0% | 0 | 890
Water Filter Cartridge | 420 | 0 | 420 | Was 1xspringflow, Northcote Int but now Ivoclar vivadent 297563 Lise Dem 32 Resin cartiridge Pkt 4 |  | 0% | 0 | 0% | 0 | 420
Compressed air | 10702 | 0 | 10702 | Ivoclar vivadent Ltd but DHB direct to Cattani | Cattani K300 x2 | 0% | 0 | 0% | 0 | 10702
Suction/Amalgam Margin .08% Separator Turbosmart A | 16160 | 0 | 16160 | Cattani ISO 11143 Direct DHB via Ivoclar | ISO Amalgam Separators x2 | 0% | 0 | 0% | 0 | 16160
Washer | 9219 | 0 | 9219 | Steelco DS50DRSD Benchtop Plus includes the Installation | Mercer Medical Equipment | 0% | 0 | 0% | 0 | 9219
Oiling Unit for Hand Pieces | 0 | 0 | 0 | NSK N/A until using NSK handpieces | No Oiling - Belinda to Add Kavo Later | 0% | 0 | 0% | 0 | 0
Filling trays , Preventive trays, Examination trays (awaiting quote) HCE | 1475.28 | 0 | 1475.28 | 12 x 10 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1475.28
| 2290.32 | 0 | 2290.32 | 18x7 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 2290.32
| 1216.56 | 0 | 1216.56 | 12x 5 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1216.56
| 900 | 0 | 900 | Carparking/Yard |  | 0% | 0 | 0% | 0 | 900
| 900 | 0 | 900 | Freight & installation |  | 0% | 0 | 0% | 0 | 900
| 54846 | 0 | 54846 | 12 Oclock | Units from DentalEZ | 0% | 0 | 0% | 0 | 54846
Miscellaneouls
Danbar Chairs
FITOUT TOTAL | 144748.16 | 0 | 144748.16 | Fitout Sub Total |  | 0 | 0 | 0 | 0 | 144748.16
Provisional Sum 1
Provisional Sum 2
Provisional Sum 3
Local Authority per Site | 5454 | 0 | 5454 | Council Fees | Waitakere City Council | 29.91% | 1631.53 | 41.48% | 631.05 | 3191.42
| 8000 | 0 | 8000 | Contractor Margin |  | 0% | 0 | 0 | 0 | 8000
| 40000 | 0 | 40000 | Contingency |  | 0% | 0 | 0 | 0 | 40000
FITOUT TOTAL | 144748.16 | 0 | 144748.16 | Fitout Sub Total |  | 0 | 0 | 0 | 0 | 144748.16
Allowed for as Building Plant
Note 1: Claims by contractors may be by percentages but claims by Consultants may be in Actual costs
Glenfield Intermediate School 4 Chair Clinic
WDHB Oral | [5 empty] | Ex GST @ 12.5%
|  |  |  | Date This Report | 2010-07-01 | Actual Spend to Date
CLINICAL | Clinics - Bayview; Manukau; Beachhaven; Birkdale Intermediate; Birkdale North; Northcotes Intermediate; Target Road; Northcote School;Willow Park;
BUILDING
Dental Chairs Existing | 0 | 0 | 0 | 2X Royal GP11's (Target Rd); 2x Royals (Willow Park) |  | 0% | 0 | 0% | 0 | 0 | ( 2x Royal Gp 11, Bruce McLaren, 1x Royal Arahoe, 1x Royal WHL09608 Manakau Prim )
Operating light | 0 | 0 | 0 | (2x Faro s 2000, NSH 51878A, no number, Rutherford prim, 2xFaro s 2000, Glendene) |  | 0% | 0 | 0% | 0 | 0
Dental Chairs New Adec 500 Chair (Plus assistant stool minus assistant arm) | 0 | 0 | 0 | Resused |  | 0% | 0 | 0% | 0 | 0
Dental Carts/Units | 0 | 0 | 0 | ( 2x DCI DM4 Carts, WHL06085, WHA210020, Western Heights, 1x DM4 WHSA200477 Beachhaven, 1x DCI DM4, Arahoe) |  | 0% | 0 | 0% | 0 | 0
Autoclave (statim) | 0 | 0 | 0 | (1X Statim, S2000 Arahoe, 1x Statim S2000, Bruce McLaren) |  | 0% | 0 | 0% | 0 | 0
Lisa (B Class) | 0 | 0 | 0 | W&H Lisa517 | Ivoclar vivadent Ltd | 0% | 0 | 0% | 0 | 0
Xray Machine | 0 | 0 | 0 | x1 Kodak 2200, Henderson North |  | 0% | 0 | 0% | 0 | 0
Xray developer | 0 | 0 | 0 | x1 Durr Periomat, henderson North |  | 0% | 0 | 0% | 0 | 0
Curing Light | 0 | 0 | 0 | x3 Demi Curing Light (Already Purchasedd) |  | 0% | 0 | 0% | 0 | 0
Amalgamator | 0 | 0 | 0 | FO3160 (Already Purchased) |  | 0% | 0 | 0% | 0 | 0
Water Filter Demonizing Unit | 890 | 0 | 890 | Was already ordered but it now Ivoclar vivadent 297563 Lise Dem 32 Demonizing unit |  | 0% | 0 | 0% | 0 | 890
Water Filter Cartridge | 420 | 0 | 420 | Was already ordered but now Ivoclar vivadent 297563 Lise Dem 32 Resin cartiridge Pkt 4 |  | 0% | 0 | 0% | 0 | 420
Compressed air | 5325 | 0 | 5325 |  | Cattani K300 x1 | 0% | 0 | 0% | 0 | 5325
Suction/Amalgam Separator Turbosmart B | 9815 | 0 | 9815 | Cattani ISO 11143 Direct DHB to Ivoclar | ISO Amalgam Separator x1 off | 0% | 0 | 0% | 0 | 9815
Washer | 9219 | 0 | 9219 | Steelco DS50DRSD Benchtop Plus includes the Installation | Mercer Medical Equipment | 0% | 0 | 0% | 0 | 9219
Oiling Unit for Hand Pieces -To Go Under Bench in the Reprocessing Room | 5000 | 0 | 5000 | NSK N/A until using NSK handpieces | Oiling Unit Required - Dentalectra to Quote | 0% | 0 | 0% | 0 | 5000
Filling trays , Preventive trays, Examination trays (awaiting quote) HCE | 1475.28 | 0 | 1475.28 | 12 x 10 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1475.28
| 2290.32 | 0 | 2290.32 | 18x7 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 2290.32
| 1216.56 | 0 | 1216.56 | 12x 5 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1216.56
| 900 | 0 | 900 | Carparking/Yard |  | 0% | 0 | 0% | 0 | 900
| 900 | 0 | 900 | Freight & installation |  | 0% | 0 | 0% | 0 | 900
| 36644 | 0 | 36644 | 12 Oclock | Units from DentalEZ | 0% | 0 | 0% | 0 | 36644
Miscellaneouls
Danbar Chairs
FITOUT TOTAL | 74095.16 | 0 | 74095.16 | Fitout Sub Total |  | 0 | 0 | 0 | 0 | 74095.16
Edmonton Primary School 2 Chair Clinic
WDHB Oral | [5 empty] | Ex GST @ 12.5%
|  |  |  | Date This Report | 2010-07-01 | Actual Spend to Date
CLINICAL | Clinic Closures - Henderson North; Summerland; Freyberg; Arahoe; Western Hts; Bruce McLaren; Henderson South; Henderson School; Peninsula; Pomaria; Rutherford; Te Atatu Int; Birwood; Doln Buck; Massey;\ Ranui;
BUILDING
Dental Chairs Existing | 0 | 0 | 0 | 2x New Adec 500 Chairs |  | 0% | 0 | 0% | 0 | 0
Operating light | 0 | 0 | 0 | 2X ADEC Chair or ceiling mountedLights |  | 0% | 0 | 0% | 0 | 0
Dental Chairs New Adec 500 Chair (Plus assistant stool minus assistant arm) | 38520 | 0 | 38520 | Adec 500 chair /light (minus assistant stool minus assistance arm) | Ivoclar vivadent Ltd | 0% | 0 | 0% | 0 | 38520
Dental Carts/Units | 0 | 0 | 0 | Resuse existing Carts; Post Drill to Ensure Chairs and Carts services come up at foot of chairs. |  | 0% | 0 | 0% | 0 | 0
Autoclave (statim) | 0 | 0 | 0 | ( 1x Staim s 2000 Edmonton Remains) |  | 0% | 0 | 0% | 0 | 0
Lisa (B Class) | 0 |  |  | NA to 2 Chair |  | 0% | 0 | 0% | 0 | 0
Xray Machine | 0 | 0 | 0 | 1x Ardet Pamotine (Edmonton, remain) |  | 0% | 0 | 0% | 0 | 0
Xray developer | 0 | 0 | 0 | 1x Durr Periomat (Edmonton, remains) |  | 0% | 0 | 0% | 0 | 0
Curing Light | 0 | 0 | 0 | 2x SDI LED Cordless Curing Light Edmonton remains) |  | 0% | 0 | 0% | 0 | 0
Amalgamator Existing | 0 | 0 | 0 | NA |  | 0% | 0 | 0% | 0 | 0
Amalgamator New | 1530 | 0 | 1530 | Satelec FO3160 | Gunz dental | 0% | 0 | 0% | 0 | 1530
Water Filter Demonizing Unit | 890 | 0 | 890 | Was 1xspringflow, Northcote Int but it now Ivoclar vivadent 297563 Lise Dem 32 Demonizing unit |  | 0% | 0 | 0% | 0 | 890
Water Filter Cartridge | 420 | 0 | 420 | Was 1xspringflow, Northcote Int but now Ivoclar vivadent 297563 Lise Dem 32 Resin cartiridge Pkt 4 |  | 0% | 0 | 0% | 0 | 420
Compressed air | 4428 | 0 | 4428 | Ivoclar vivadent Ltd but DHB order direct Cattanni | Cattani K200 x1 | 0% | 0 | 0% | 0 | 4428
Suction/Amalgam Separator Turbosmart A | 8080 | 0 | 8080 | Cattani ISO 11143 Direct DHB to Ivoclar | ISO Amalgam Separator | 0% | 0 | 0% | 0 | 8080
[6 empty] | 0% | 0 | 0% | 0 | 0
Washer plus installation | 0 | 0 | 0 | Steelco DS50DRSD Benchtop Plus includes the Installation | Mercer Medical Equipment - No washers for 2 and 3 chair | 0% | 0 | 0% | 0 | 0
Oiling Unit for Hand Pieces | 0 | 0 | 0 | NSK N/A until using NSK handpieces | No Oiling - Belinda to Add Kavo Later | 0% | 0 | 0% | 0 | 0
Filling trays , Preventive trays, Examination trays (awaiting quote) HCE | 1967.04 | 0 | 1967.04 | 16 x 10 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1967.04
| 3053.76 | 0 | 3053.76 | 24x7 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 3053.76
| 1622.08 | 0 | 1622.08 | 16x 5 set | Hu Freidy Quote | 0% | 0 | 0% | 0 | 1622.08
| 900 | 0 | 900 | Carparking/Yard |  | 0% | 0 | 0% | 0 | 900
| 900 | 0 | 900 | Freight & installation |  | 0% | 0 | 0% | 0 | 900
12 Oclocks | 18322 | 0 | 18322 | Ordered incl Freight | Units from DentalEZ | 0% | 0 | 0% | 0 | 18322
Miscellaneouls
Danbar Chairs
FITOUT TOTAL | 80632.88 | 0 | 80632.88 | Fitout Sub Total |  | 0 | 0 | 0 | 0 | 80632.88