## BOT Lease Works
FIXED-TRANSPORTABLE PAD SURVEYS
ORAL HEALTH BUSINESS CASE
Woods/Coffey Topographical Survey Chart & Costs
DM Change From Diagnostic to Driveable >
Add New Fixed Facility Clinic
Add New Transportable Pad
<Rod Progress - Work been completed adequately
<Rod Progress - Sites Instructed to Woods to carry out Topo Survey
<Rod Progress - Sites Instructed to Coffey to carry out Geotech Survey
<Rod Progress - Sites instructed to Woods and Coffey for both Topo and Geotech Surveys
<Dental Manager Change of Cluster and Treatment Type
<Contributing Schools only - No pad required - yet
<Checked as staying in same cluster as at November 09
<Move into new cluster
<change Dianostic to full treatment
<change Full Treatment to diagnistic
< Cost Changes in Design
| Location | Unique ID Reference to all Pad Sites | Pad Survey | Lease Conditions | Comments
PHASE 1
CENTRAL NORTH SHORE CLUSTER
FIXED CLINIC
| GLENFIELD INTERMEDIATE | 1-CNS-F1 | Yes | Tender
DIAGNOSTIC PORTABLE
| BAYVIEW SCHOOL | 1-CNS-D1 | Yes | Conditions ready to draw up BOT Leases for approval
| GLENFIELD PRIMARY SCHOOL | 1-CNS-D2 | Yes | Conditions ready to draw up BOT Leases for approval
| MANUKA PRIMARY SCHOOL | 1-CNS-D3 | Yes | Conditions ready to draw up BOT Leases for approval
| MARLBOROUGH SCHOOL | 1-CNS-D4 | Yes | Conditions ready to draw up BOT Leases for approval
| SUNNYBRAE NORMAL SCHOOL | 1-CNS-D5 | Yes | Conditions ready to draw up BOT Leases for approval
| WAIRAU VALLEY SCHOOL | 1-CNS-D6 |  | Will come up to the Hub Glenfield Int
| WINDY RIDGE SCHOOL | 1-CNS-D7 | Yes | Conditions ready to draw up BOT Leases for approval
| CHELSEA SCHOOL | 1-CNS-D8 | Yes | Conditions ready to draw up BOT Leases for approval
| KAURI PARK SCHOOL | 1-CNS-D9 | Yes | Conditions ready to draw up BOT Leases for approval
| NORTHCOTE SCHOOL | 1-CNS-D10 | Yes | Conditions ready to draw up BOT Leases for approval
| ST MARY'S SCHOOL (NORTHCOTE) | 1-CNS-D11 | Yes | Conditions ready to draw up BOT Leases for approval
| VERRAN SCHOOL | 1-CNS-D12 | Yes | Conditions ready to draw up BOT Leases for approval
| WILLOWPARK SCHOOL | 1-CNS-D13 | Yes | Conditions ready to draw up BOT Leases for approval
| WESTMINSTER CHRISTIAN SCHOOL | 1-A-D9 | Yes | Conditions ready to draw up BOT Leases for approval
TREATMENT PORTABLE
| BEACH HAVEN SCHOOL | 1-CNS-T1 | Yes | Conditions ready to draw up BOT Leases for approval
| BIRKDALE INTERMEDIATE | 1-CNS-T2 | Yes | Conditions ready to draw up BOT Leases for approval
| BIIRKDALE NORTH SCHOOL | 1-CNS-T3 | Yes | Conditions ready to draw up BOT Leases for approval
| BIRKDALE PRIMARY | 1-CNS-T4 | Yes | Conditions ready to draw up BOT Leases for approval
| NORTHCOTE INTERMEDIATE (ONEPOTO) (HOLD) | 1-CNS-T5 | Yes | Conditions ready to draw up BOT Leases for approval
| TARGET ROAD SCHOOL Invoice 00314686 | 1-CNS-T6 | Yes | Conditions ready to draw up BOT Leases for approval
| TKKM O TE RAKI PAEWHENUA (Now Treatment) | 2-ED-DFT15 |  | Visit Required
ALBANY CLUSTER
Modify Plan (more my be required for BOT MOE approv)
DIAGNOSTIC PORTABLE
| ALBANY JUNIOR HIGH SCHOOL (IF NOT FIXED) | 1-A-D1 | Yes | Conditions ready to draw up BOT Leases for approval
| ALBANY SCHOOL | 1-A-D2 | Yes | Conditions ready to draw up BOT Leases for approval
| COATESVILLE SCHOOL | 1-A-D3 | Yes | Conditions ready to draw up BOT Leases for approval
| GREENHITHE SCHOOL | 1-A-D4 | Yes | Conditions ready to draw up BOT Leases for approval
| KRISTIN SCHOOL | 1-A-D5 |  | Visit Required
| PINEHURST SCHOOL | 1-A-D6 | Yes | Conditions ready to draw up BOT Leases for approval
| RIDGEVIEW SCHOOL | 1-A-D7 |  | Visit Required
| UPPER HARBOUR PRIMARY SCHOOL | 1-A-D8 | Yes | Conditions ready to draw up BOT Leases for approval
HENDERSON / WAITAKERE / TE ATATU CLUSTER
FIXED CLINIC
| HENDERSON INTERMEDIATE | 1-HWT-F1 | Yes | Conditions ready to draw up BOT Leases for approval
| EDMONTON SCHOOL | 1-HWT-F2 | Yes | Conditions ready to draw up BOT Leases for approval
DIAGNOSTIC PORTABLE
| HENDERSON NORTH SCHOOL | 1-HWT-D1 | Yes | Conditions ready to draw up BOT Leases for approval
| NGA KAKANO CHRISTIAN REO RUA KURA | 1-HWT-D2 |  | Will go up to Henderson Int
| SUMMERLAND PRIMARY | 1-HWT-D3 | Yes | Conditions ready to draw up BOT Leases for approval
| WESTERN HEIGHTS SCHOOL (AUCKLAND) | 1-HWT-D4 | Yes | Conditions ready to draw up BOT Leases for approval
| FREYBERG COMMUNITY SCHOOL | 1-HWT-D5 | Yes | Conditions ready to draw up BOT Leases for approval
| RANGEVIEW INTERMEDIATE | 1-HWT-D6 | Yes | Conditions ready to draw up BOT Leases for approval
| Revisit Rangeview (Principal has new location) |  |  | Rod to Review and Visit Adjacent Reserve with WCC
| TIRIMOANA SCHOOL | 1-HWT-D7 | Yes | Conditions ready to draw up BOT Leases for approval
| FLANSHAW SCHOOL | 1-HWT-FTD3 | Yes | Conditions ready to draw up BOT Leases for approval
TREATMENT PORTABLE
| ARAHOE SCHOOL | 1-HWT-T1 | Yes | Review and Visit
| Revisit Arahoe School |  |  | Review and Visit
| BRUCE MCLAREN INTERMEDIATE (WAITAKERE) | 1-HWT-T2 | Yes | Conditions ready to draw up BOT Leases for approval
| HENDERSON PRIMARY SCHOOL | 1-HWT-T4 | Yes | Conditions ready to draw up BOT Leases for approval
| HENDERSON SOUTH SCHOOL | 1-HWT-T5 | Yes | Conditions ready to draw up BOT Leases for approval
| HENDERSON VALLEY SCHOOL | 1-HWT-T6 | Yes | Conditions ready to draw up BOT Leases for approval
| MATIPO ROAD SCHOOL (HOLD) | 1-HWT-T7 | Hold | Review and Visit
| PENINSULA PRIMARY SCHOOL | 1-HWT-T8 | Yes | Conditions ready to draw up BOT Leases for approval
| POMARIA ROAD SCHOOL | 1-HWT-T9 | Yes | Conditions ready to draw up BOT Leases for approval
| RUTHERFORD SCHOOL (TKKIM OTE KOTUKU) | 1-HWT-T10 | Yes | Conditions ready to draw up BOT Leases for approval
| TE ATATU INTERMEDIATE | 1-HWT-T11 | Yes | Conditions ready to draw up BOT Leases for approval
| TKKM O HOANI WAITITI | 3-GK-T5 |  | Review and Visit
CONTRIBUTING SCHOOL TO HENDERSON INT
| JIREH SCHOOL | 1-HWT-X1 |  | No pad Required
| LISTON COLLEGE | 1-HWT-X2 | No' | No pad Required
| ST DOMINIC'S COLLEGE (HENDERSON) | 1-HWT-X3 | No' | No pad Required
| SUNDERLAND SCHOOL AND COLLEGE | 1-HWT-X4 | No' | No pad Required
NEW LYNN / GENDENE CLUSTER CLUSTER
TREATMENT PORTABLE
| FRUITVALE ROAD SCHOOL | 2-NG-T1 | Yes | Conditions ready to draw up BOT Leases for approval
| GLENDENE SCHOOL (WEST CITY CHRISTIAN) | 2-NG-T2 | Yes | Conditions ready to draw up BOT Leases for approval
| KELSTON INTERMEDIATE | 2-NG-T3 AND 2-NG-T6 = 1 PAD | Yes | Conditions ready to draw up BOT Leases for approval
ST LEONARDS ROAD SCHOOL
| KELSTON PRIMARY (KELSTON DEAF EDUCATION) | 2-NG-T4 | Yes | Conditions ready to draw up BOT Leases for approval
| NEW LYNN SCHOOL (OAKLYNN SPECIAL) | 2-NG-T5 | Yes | Conditions ready to draw up BOT Leases for approval
#VALUE!
PHASE 2
| FIXED 3 CHAIR CLINIC AT ALBANY JUNIOR HIGH | 1-A-F3 | Yes | Conditions ready to draw up BOT Leases for approval
| BIRKENHEAD SCHOOL | 1-CNS-F2 | Yes | Conditions ready to draw up BOT Leases for approval
EAST COAST BAYS / DEVONPORT CLUSTER
FIXED CLINIC
| BELMONT INTERMEDIATE | 2-ED-F1 | Yes | Lease to be Drawn up
| FORREST HILL SCHOOL | 2-ED-F2 | Yes | Conditions ready to draw up BOT Leases for approval
Coffey On Site Services Location 0116028 Incl 1550 x2
Coffey Liquid Limit Field Testing 0116028
Coffey Disbursements 0116028
DIAGNOSTIC PORTABLE
| BAYSWATER SCHOOL | 2-ED-D1
| BELMONT SCHOOL (AUCKLAND) | 2-ED-D2 |  | Have Visited School - Survey Required
| DEVONPORT SCHOOL | 2-ED-D3 |  | Have Visited School - Survey Required
| HAURAKI SCHOOL | 2-ED-D4
| ST LEOS SCHOOL (DEVONPORT) | 2-ED-D5
| STANLEY BAY SCHOOL | 2-ED-D6 |  | Have Visited School - Survey Required
| VAUXHALL SCHOOL | 2-ED-D7 |  | Have Visited School - Survey Required
| CARMEL COLLEGE | 2-ED-D8
| MILFORD SCHOOL (AUCKLAND) | 2-ED-D9
| ROSMINI COLLEGE | 2-ED-D10
| ST JOSEPH'S SCHOOL (TAKAPUNA) | 2-ED-D11 |  | visited - survey required 17/5/2010
| SUNNYNOOK SCHOOL | 2-ED-D12
| TAKAPUNA NORMAL INTERMEDIATE | 2-ED-D13
| TAKAPUNA SCHOOL | 2-ED-D14
| WAIRAU INTERMEDIATE | 2-ED-D16 |  | visited - survey required 17/5/2010
UNKNOWN TYPE
| APPLE TREE EDUCATION CENTRE | 2-ED-X1 |  | No Pad Required
| WILSON SCHOOL | 2-ED-X2 |  | No Pad Required
PINEHILL / LONG BAY CLUSTER
FIXED CLINIC
| NORTHCROSS INTERMEDIATE | 2-PL-D6 | 1550 | Lease Required
DIAGNOSTIC PORTABLE
| BROWNS BAY SCHOOL | 2-PL-D1
| CAMPBELLS BAY SCHOOL | 2-PL-D2 |  | Ready to Survey
| GLAMORGAN SCHOOL | 2-PL-D3 |  | Ready to Survey
| LONG BAY SCHOOL | 2-PL-D4
| MAIRANGI BAY SCHOOL | 2-PL-D5 | COMBINE PADS | visited - survey required 17/5/2010 | potentuial problem with site contour - surveyors to confirm
| MURRAYS BAY INTERMEDIATE | 2-PL-F1
| MURRYS BAY PRIMARY SCHOOL | 2-PL-X2
| OTEHA VALLEY SCHOOL | 2-PL-D7
| PINEHILL SCHOOL (BROWNS BAY) | 2-PL-D8 |  | visited - survey required 17/5/2010
| SHERWOOD SCHOOL (AUCKLAND) | 2-PL-D9
| ST JOHN'S SCHOOL (MAIRANGI BAY) | 2-PL-D10
| TORBAY SCHOOL | 2-PL-D11
| CITY IMPACT CHURCH SCHOOL | 2-PL-X1 |  | No Pad Required
| THE CORELLI SCHOOL | 2-PL-X3 |  | No Pad Required
OREWA / MANLY CLUSTER
FIXED CLINIC
| RED BEACH SCHOOL | 3-OM-F1 |  | Visit and Survey
DIAGNOSTIC PORTABLE
| KINGSWAY SCHOOL | 3-OM-D1
| OREWA COLLEGE | 3-OM-D2
| OREWA NORTH SCHOOL | 3-OM-D3
| OREWA SCHOOL | 3-OM-D4
| SILVERDALE SCHOOL | 3-OM-D5
| STELLA MARIS PRIMARY SCHOOL | 3-OM-D6
| WAINUI SCHOOL | 3-OM-FTD6
TREATMENT PORTABLE
| DAIRY FLAT SCHOOL | 3-OM-T1
| GULF HARBOUR SCHOOL | 3-OM-T2
| MATAKANA SCHOOL (LEIGH) | 3-OM-T4
| STANMORE BAY SCHOOL | 3-OM-T5
| WHANGAPAROA SCHOOL | 3-OM-T7
| WHANGAPAROA COLLEGE | 3-OM-T8
PHASE 3
Transportable Treatment Slab at Warkworth
NORTH RODNEY CLUSTER
TREATMENT PORTABLE
| AHUROA SCHOOL | 3-NR-T1
| KAIPARA FLATS SCHOOL | 3-NR-T2
| MAHURANGI CHRISTIAN SCHOOL | 3-NR-T3
| PAKIRI SCHOOL | 3-NR-T4
| SNELLS BEACH | 3-NR-T5
| TAPORA SCHOOL | 3-NR-T6
| TAUHOA SCHOOL | 3-NR-T7
| TOMARATA SCHOOL | 3-NR-T8
| WARKWORTH SCHOOL | 3-NR-T9
| WELLSFORD SCHOOL | 3-NR-T10
| MAHURANGI COLLEGE | 3-OM-T3
| LIVING WAY LEARNING CENTRE | 3-OM-X1
GLEN EDEN / KAREKARE CLUSTER
FIXED CLINIC
| GLEN EDEN INTERMEDIATE | 3-GK-D1
DIAGNOSTIC PORTABLE
| KAURILANDS SCHOOL TBA | 3-GK-F1
| GREEN BAY PRIMARY | 3-GK-D2
| KONINI SCHOOL (AUCKLAND) | 3-GK-D3
| LAINGHOLM SCHOOL | 3-GK-D4
| TITIRANGI SCHOOL | 3-GK-D5
| WOODLANDS PARK SCHOOL | 3-GK-D6
Woods Disbursement Land on Line Charges
TREATMENT PORTABLE
| HOLY CROSS SCHOOL (HENDERSON) (New Pad) | 3-GK-T1
| ORATIA SCHOOL | 3-GK-T2
| PROSPECT SCHOOL | 3-GK-T3
| SUNNYVALE SCHOOL | 3-GK-T4
| GLEN EDEN PRIMARY SCHOOL | 3-GK-T6
CONTRIBUTER TO KAURILANDS SCHOOL
| TITIRANGI RUDOLF STEINER SCHOOL | 3-GK-X1
SOUTH RODNEY CLUSTER
DIAGNOSTIC DRIVEABLE - Put Pad Down TBC?
| TAU TE AROHANOA AKORANGA | 3-SR-DRVD1
| WAIONEKE SCHOOL | 3-SR-DRVD2
| WAITOKI SCHOOL | 3-SR-DRVD3
| WOODHILL SCHOOL | 3-SR-DRVD4
TREATMENT PORTABLE
| HELENSVILLE SCHOOL | 3-SR-T1
| KAUKAPAKAPA SCHOOL (WAITOKI) | 3-SR-T2
| PARAKAI SCHOOL | 3-SR-T3
| WAIMAUKU SCHOOL (WOODHILL) | 3-SR-T4
WESTGATE / WEST CLUSTER CLUSTER
FIXED CLINIC
| DON BUCK SCHOOL | 1-RS-T2
DIAGNOSTIC PORTABLE
| HOBSONVILLE SCHOOL | 2-WW-D1
| MARINA VIEW SCHOOL | 2-WW-D2
| ROYAL ROAD SCHOOL | 2-WW-D3
| ST PAUL'S SCHOOL (MASSEY) | 2-WW-D4
| WEST HARBOUR SCHOOL | 2-WW-D5
| WESTBRIDGE RESIDENTIAL SCHOOL | 2-WW-D6
| WHENUAPAI SCHOOL | 2-WW-D7
| COLWILL SCHOOL | 2-WW-D8
| HUAPAI DISTRICT SCHOOL | 2-WW-D9
| LINCOLN HEIGHTS SCHOOL | 2-WW-D10
| RIVERHEAD SCHOOL | 2-WW-D11
CONTRIBUTING SCHOOL TO WESTGATE FIXED
| HARE KRISHNA SCHOOL | 2-WW-X1
| TIMATANGA COMMUNITY SCHOOL | 2-WW-X2
RANUI / SWANSON CLUSTER
TREATMENT PORTABLE
| BIRWOOD SCHOOL | 1-RS-T1
| WESTGATE | 3-WW-F1
| MASSEY PRIMARY SCHOOL | 1-RS-T3
| RANUI SCHOOL | 1-RS-TT
| SWANSON SCHOOL | 1-RS-T5
| TAUPAKI SCHOOL | 1-RS-T6
| WAITAKERE SCHOOL | 1-RS-T6

## Phase 1 Clinic Equip
FIXED-TRANSPORTABLE PAD SURVEYS
ORAL HEALTH BUSINESS CASE
| Location | Unique ID Reference to all Pad Sites | Clinics To Close | Clinics being Surveyed
PHASE 1
CENTRAL NORTH SHORE CLUSTER
FIXED CLINIC
| GLENFIELD INTERMEDIATE | 1-CNS-F1 |  | Glenfield Int
| BIRKENHEAD SCHOOL | 1-CNS-F2
Modify Plan - New Layout (may be more changes)
Allow for Woods WDHB Regional Map showing Sites
DIAGNOSTIC PORTABLE
| BAYVIEW SCHOOL | 1-CNS-D1 | Bayview; | Bayview Primary
| GLENFIELD PRIMARY SCHOOL | 1-CNS-D2
| MANUKA PRIMARY SCHOOL | 1-CNS-D3 | Manuka; | Manuka;
| MARLBOROUGH SCHOOL | 1-CNS-D4
| SUNNYBRAE NORMAL SCHOOL | 1-CNS-D5
| WAIRAU VALLEY SCHOOL | 1-CNS-D6
| WINDY RIDGE SCHOOL | 1-CNS-D7
| CHELSEA SCHOOL | 1-CNS-D8
| KAURI PARK SCHOOL | 1-CNS-D9
| NORTHCOTE SCHOOL | 1-CNS-D10 | Northcote School | Northcote Primary
| ST MARY'S SCHOOL (NORTHCOTE) | 1-CNS-D11
| VERRAN SCHOOL | 1-CNS-D12
| WILLOWPARK SCHOOL | 1-CNS-D13 | Willow Park | Willow Park
Revisit Willow Park
| WESTMINSTER CHRISTIAN SCHOOL | 1-A-D9
TREATMENT PORTABLE
| BEACH HAVEN SCHOOL | 1-CNS-T1 | Beachhaven | Beachhaven;
| BIRKDALE INTERMEDIATE | 1-CNS-T2 | Birkdale Intermediate; | Birkdale Intermediate;
| BIIRKDALE NORTH SCHOOL | 1-CNS-T3 | Birkdale North; | Birkdale North;
| BIRKDALE PRIMARY | 1-CNS-T4
| NORTHCOTE INTERMEDIATE (ONEPOTO) (HOLD) | 1-CNS-T5 | Northcotes Int | Northcote Int
| TARGET ROAD SCHOOL (HOLD) | 1-CNS-T6 | Target Road | Target Road Primary
| TKKM O TE RAKI PAEWHENUA (Now Treatment) | 2-ED-DFT15
ALBANY CLUSTER
| FIXED 3 CHAIR CLINIC AT ALBANY JUNIOR HIGH | 1-A-F3
Modify Plan (more my be required for BOT MOE approv)
DIAGNOSTIC PORTABLE
| ALBANY JUNIOR HIGH SCHOOL (IF NOT FIXED) | 1-A-D1
| ALBANY SCHOOL | 1-A-D2 | Albany Primary
| COATESVILLE SCHOOL | 1-A-D3
| GREENHITHE SCHOOL | 1-A-D4 | Greenhithe
| KRISTIN SCHOOL | 1-A-D5
| PINEHURST SCHOOL | 1-A-D6
| RIDGEVIEW SCHOOL | 1-A-D7
| UPPER HARBOUR PRIMARY SCHOOL | 1-A-D8
HENDERSON / WAITAKERE / TE ATATU CLUSTER
FIXED CLINIC
| HENDERSON INTERMEDIATE | 1-HWT-F1 | Henderson Int
| EDMONTON SCHOOL | 1-HWT-F2 | Edmonton Prim
DIAGNOSTIC PORTABLE
| HENDERSON NORTH SCHOOL | 1-HWT-D1 | Henderson North;
| NGA KAKANO CHRISTIAN REO RUA KURA | 1-HWT-D2
| SUMMERLAND PRIMARY | 1-HWT-D3 | Summerland;
| WESTERN HEIGHTS SCHOOL (AUCKLAND) | 1-HWT-D4 | Western Hts; | Western Hts;
| FREYBERG COMMUNITY SCHOOL | 1-HWT-D5 | Freyberg | Freyberg
| RANGEVIEW INTERMEDIATE | 1-HWT-D6
Revisit Rangeview (Principal has new location)
| TIRIMOANA SCHOOL | 1-HWT-D7
| FLANSHAW SCHOOL | 1-HWT-FTD3
TREATMENT PORTABLE
| ARAHOE SCHOOL | 1-HWT-T1 | Arahoe;
Revisit Arahoe School
| BRUCE MCLAREN INTERMEDIATE (WAITAKERE) | 1-HWT-T2 | Bruce McLaren;
| HENDERSON SCHOOL | 1-HWT-T4 | Henderson School
Revisit Henderson Primary
| HENDERSON SOUTH SCHOOL | 1-HWT-T5 | Henderson South;
| HENDERSON VALLEY SCHOOL | 1-HWT-T6
| MATIPO ROAD SCHOOL (HOLD) | 1-HWT-T7
| PENINSULA PRIMARY SCHOOL | 1-HWT-T8 | Peninsula;
| POMARIA ROAD SCHOOL | 1-HWT-T9 | Pomaria;
| RUTHERFORD SCHOOL (TKKIM OTE KOTUKU) | 1-HWT-T10 | Rutherford; | Rutherford;
| TE ATATU INTERMEDIATE | 1-HWT-T11 | Te Atatu Int; | Te Atatu Int
| TKKM O HOANI WAITITI | 3-GK-T5
CONTRIBUTING SCHOOL TO HENDERSON INT
| JIREH SCHOOL | 1-HWT-X1
| LISTON COLLEGE | 1-HWT-X2
| ST DOMINIC'S COLLEGE (HENDERSON) | 1-HWT-X3
| SUNDERLAND SCHOOL AND COLLEGE | 1-HWT-X4
NEW LYNN / GENDENE CLUSTER CLUSTER
TREATMENT PORTABLE
| FRUITVALE ROAD SCHOOL | 2-NG-T1
| GLENDENE SCHOOL (WEST CITY CHRISTIAN) | 2-NG-T2 | Glendene
| KELSTON INTERMEDIATE | 2-NG-T3
| KELSTON SCHOOL (KELSTON DEAF EDUCATION) | 2-NG-T4 | Kelston Primary
| NEW LYNN SCHOOL (OAKLYNN SPECIAL) | 2-NG-T5 | New Lynn
| ST LEONARDS ROAD SCHOOL | 2-NG-T6 | St Leonards
PHASE 2
EAST COAST BAYS / DEVONPORT CLUSTER
FIXED CLINIC
| BELMONT INTERMEDIATE | 2-ED-F1
| FORREST HILL SCHOOL | 2-ED-F2
DIAGNOSTIC PORTABLE
| BAYSWATER SCHOOL | 2-ED-D1
| BELMONT SCHOOL (AUCKLAND) | 2-ED-D2
| DEVONPORT SCHOOL | 2-ED-D3
| HAURAKI SCHOOL | 2-ED-D4
| ST LEOS SCHOOL (DEVONPORT) | 2-ED-D5
| STANLEY BAY SCHOOL | 2-ED-D6
| VAUXHALL SCHOOL | 2-ED-D7
| CARMEL COLLEGE | 2-ED-D8
| MILFORD SCHOOL (AUCKLAND) | 2-ED-D9
| ROSMINI COLLEGE | 2-ED-D10
| ST JOSEPH'S SCHOOL (TAKAPUNA) | 2-ED-D11
| SUNNYNOOK SCHOOL | 2-ED-D12
| TAKAPUNA NORMAL INTERMEDIATE | 2-ED-D13
| TAKAPUNA SCHOOL | 2-ED-D14
| WAIRAU INTERMEDIATE | 2-ED-D16
UNKNOWN TYPE
| APPLE TREE EDUCATION CENTRE | 2-ED-X1
| WILSON SCHOOL | 2-ED-X2
PINEHILL / LONG BAY CLUSTER
FIXED CLINIC
| NORTHCROSS INTERMEDIATE | 2-PL-D6
DIAGNOSTIC PORTABLE
| MURRAYS BAY INTERMEDIATE | 2-PL-F1
| BROWNS BAY SCHOOL | 2-PL-D1
| CAMPBELLS BAY SCHOOL | 2-PL-D2
| GLAMORGAN SCHOOL | 2-PL-D3
| LONG BAY SCHOOL | 2-PL-D4
| MAIRANGI BAY SCHOOL | 2-PL-D5
| OTEHA VALLEY SCHOOL | 2-PL-D7
| PINEHILL SCHOOL (BROWNS BAY) | 2-PL-D8
| SHERWOOD SCHOOL (AUCKLAND) | 2-PL-D9
| ST JOHN'S SCHOOL (MAIRANGI BAY) | 2-PL-D10
| TORBAY SCHOOL | 2-PL-D11
| CITY IMPACT CHURCH SCHOOL | 2-PL-X1
| MURRYS BAY SCHOOL | 2-PL-X2
| THE CORELLI SCHOOL | 2-PL-X3
WESTGATE / WEST CLUSTER CLUSTER
FIXED CLINIC
| DON BUCK SCHOOL | 1-RS-T2
DIAGNOSTIC PORTABLE
| HOBSONVILLE SCHOOL | 2-WW-D1
| MARINA VIEW SCHOOL | 2-WW-D2
| ROYAL ROAD SCHOOL | 2-WW-D3
| ST PAUL'S SCHOOL (MASSEY) | 2-WW-D4
| WEST HARBOUR SCHOOL | 2-WW-D5
| WESTBRIDGE RESIDENTIAL SCHOOL | 2-WW-D6
| WHENUAPAI SCHOOL | 2-WW-D7
| COLWILL SCHOOL | 2-WW-D8
| HUAPAI DISTRICT SCHOOL | 2-WW-D9
| LINCOLN HEIGHTS SCHOOL | 2-WW-D10
| RIVERHEAD SCHOOL | 2-WW-D11
CONTRIBUTING SCHOOL TO WESTGATE FIXED
| HARE KRISHNA SCHOOL | 2-WW-X1
| TIMATANGA COMMUNITY SCHOOL | 2-WW-X2
PHASE 3
Transportable Treatment Slab at Warkworth
NORTH RODNEY CLUSTER
TREATMENT PORTABLE
| AHUROA SCHOOL | 3-NR-T1
| KAIPARA FLATS SCHOOL | 3-NR-T2
| MAHURANGI CHRISTIAN SCHOOL | 3-NR-T3
| PAKIRI SCHOOL | 3-NR-T4
| SNELLS BEACH | 3-NR-T5
| TAPORA SCHOOL | 3-NR-T6
| TAUHOA SCHOOL | 3-NR-T7
| TOMARATA SCHOOL | 3-NR-T8
| WARKWORTH SCHOOL | 3-NR-T9
| WELLSFORD SCHOOL | 3-NR-T10
| MAHURANGI COLLEGE | 3-OM-T3
| LIVING WAY LEARNING CENTRE | 3-OM-X1
OREWA / MANLY CLUSTER
FIXED CLINIC
| RED BEACH SCHOOL | 3-OM-F1
DIAGNOSTIC PORTABLE
| KINGSWAY SCHOOL | 3-OM-D1
| OREWA COLLEGE | 3-OM-D2
| OREWA NORTH SCHOOL | 3-OM-D3
| OREWA SCHOOL | 3-OM-D4
| SILVERDALE SCHOOL | 3-OM-D5
| STELLA MARIS PRIMARY SCHOOL | 3-OM-D6
| WAINUI SCHOOL | 3-OM-FTD6
TREATMENT PORTABLE
| DAIRY FLAT SCHOOL | 3-OM-T1
| GULF HARBOUR SCHOOL | 3-OM-T2
| MATAKANA SCHOOL (LEIGH) | 3-OM-T4
| STANMORE BAY SCHOOL | 3-OM-T5
| WHANGAPAROA SCHOOL | 3-OM-T7
| WHANGAPAROA COLLEGE | 3-OM-T8
GLEN EDEN / KAREKARE CLUSTER
FIXED CLINIC
| GLEN EDEN INTERMEDIATE | 3-GK-D1
DIAGNOSTIC PORTABLE
| KAURILANDS SCHOOL TBA | 3-GK-F1
| GREEN BAY PRIMARY | 3-GK-D2
| KONINI SCHOOL (AUCKLAND) | 3-GK-D3
| LAINGHOLM SCHOOL | 3-GK-D4
| TITIRANGI SCHOOL | 3-GK-D5
| WOODLANDS PARK SCHOOL | 3-GK-D6
TREATMENT PORTABLE
| HOLY CROSS SCHOOL (HENDERSON) (New Pad) | 3-GK-T1
| ORATIA SCHOOL | 3-GK-T2
| PROSPECT SCHOOL | 3-GK-T3
| SUNNYVALE SCHOOL | 3-GK-T4
| GLEN EDEN PRIMARY SCHOOL | 3-GK-T6
CONTRIBUTER TO KAURILANDS SCHOOL
| TITIRANGI RUDOLF STEINER SCHOOL | 3-GK-X1
SOUTH RODNEY CLUSTER
DIAGNOSTIC DRIVEABLE - Put Pad Down TBC?
| TAU TE AROHANOA AKORANGA | 3-SR-DRVD1
| WAIONEKE SCHOOL | 3-SR-DRVD2
| WAITOKI SCHOOL | 3-SR-DRVD3
| WOODHILL SCHOOL | 3-SR-DRVD4
TREATMENT PORTABLE
| HELENSVILLE SCHOOL | 3-SR-T1
| KAUKAPAKAPA SCHOOL (WAITOKI) | 3-SR-T2
| PARAKAI SCHOOL | 3-SR-T3
| WAIMAUKU SCHOOL (WOODHILL) | 3-SR-T4
RANUI / SWANSON CLUSTER
TREATMENT PORTABLE
| BIRWOOD SCHOOL | 1-RS-T1
| WESTGATE | 3-WW-F1
| MASSEY PRIMARY SCHOOL | 1-RS-T3
| RANUI SCHOOL | 1-RS-TT
| SWANSON SCHOOL | 1-RS-T5
| TAUPAKI SCHOOL | 1-RS-T6
| WAITAKERE SCHOOL | 1-RS-T6