## Slide 1: CIBC5022 Site Survey Preparation and Analysis Site Reports Introduction We look at Site Reports. These are a description or a brief of the scope of works and the basis by which a construction plan for, say tendering, and the eventual winning tenderer’s site management plan is formulated.
The construction plan is not a programme. A programme is a quantifiable network or Gantt chart composed of durations to arrive at an exact completion date.
A construction plan, in contrast, is a technical essay - a written play composed only of those key scenes and players, plus onstage cast and crew, sufficient to describe the plot.
If you could summarize each act and each scene, together with their fixed and moveable background props – it may be a method statement,

## Slide 2
Example - Actors in an Operatic Scene as the consultants and Players entering and departing the Construction Site.
Example - The Cover of a NZ Resource Consent Application reused for height, breadth, depth of Temporary Building Works.

## Slide 3
Different Groups
Frequently, the person (or groups of people) preparing the plan are not the same group as those supervising and undertaking the work.
Different Times and History
This often occurs because there is a time lag between tendering / bidding for the work (when the initial plans are made) and the start of the work on site.
Different Authors
Often a supervisor arrives on site and is presented with a plan / schedule in which they had little or no involvement.

## Slide 4
Example
To re-establish key elements the earlier Traffic Plan of the development on surrounding areas is reused for Construction Traffic - Write a method statement.

## Slide 5
Example
Another check of key scenes - the Topographical Plan can be used to check the surrounding ground levels and to check the positions of Geotechnical Investigations. Write a method statement.

## Slide 6
Cost Plans Can Be Out Of Date
The plan often lacks detail or makes assumptions about the scope of work, productivity rates, work methods, resources to be used and other pertinent information.
Start and Finish Dates
It may have been assumed, for example, that the work will start during good weather, but as a result of delays in awarding the contract, commencement may not occur until after inclement season weather.
Key Resources
Furthermore, key resources assumed to be available may no longer be available and the scope of work may change between the initial plan being formulated and the start on site.

## Slide 7
Example
Check FFL’s (Finished Floor Levels), or RL’s (Reduced Levels), by observing what excavating material we require and monitoring them. Write a method statement.

## Slide 8
The Contract Documents
Many different types of plans and programmes are drawn up to cover the various aspects of the construction work.
Key Documents
Depending on the objective of your individual element or supply planning exercise, the scope of the plan or programme may vary considerably, as well as the degree of detail included between each Element or Supply.

## Slide 9
Example
The Site Setting Out Plan should show bench marks from which we can obtain site levels and check our heights and distances. Write a method statement.

## Slide 10
Components
A construction programme is a component of a construction plan. Other components of a construction plan include the:
• Health & Safety Plan
• Quality Assurance Plan
• Construction Methodology Statement

## Slide 11
Example – The floor layout plan is of major interest to the client. A method statement as to what the client will see during building operations will form Health and Safety.

## Slide 12
Example
Council Building Inspections may form Contract Deliverables for Quality Assurance.

## Slide 13
Example – The Foundation Plan may be part of our quality assurance for Guarantees. and warranties. What are the others? These could be Method Statements?

## Slide 14
The Contractual Parties
Generally, the higher up the chain of command this is intended for, the broader the view (i.e. macro level), with main activities summarised and milestones identified.
The Elemental and Trade Suppliers
Conversely with programmes prepared for site operation (i.e. micro level) use, the degree of detail increases as the practicalities of the scope of works are outlined.

## Slide 15
Logical Links in the Methodology
Look at what each component within the plan influences, and in turn, is influenced by, in terms of iteration of other components.
For example, the construction methodology influences the programme and vice versa.
Component Links
Similarly, the health and safety plan influences methodology and vice versa.
This can result in numerous circular discussions – ‘to-ing and fro-ing’ – during the development of the plan and programme.
.

## Slide 16
In summary Then For The Construction Plan:
In planning construction work there must be:
• An understanding of what has to be built;
• Establishment of the correct construction method;
• Use of the right plant and right labour to carry out the work;
• Heath and Safety considerations;
• Delivery of quality in the most economic manner; and
• Satisfaction of the Client's requirements.

## Slide 17
In Summary For the Construction Methodologies - Read The Contract Documents
Understanding what has to be built is essential and this is developed through a study of:
• Drawings;
• Specifications;
• Schedule of Quantities;
• Special Conditions of Contract;
• Statute Law, Codes and Standards; and
• Site conditions.

## Slide 18
But How Do We Communicate The Plan and its Methodology to all the Actors and Crew?
The key actors and crew are client and contractor.
We present the plan and its methodology parts at Tender to illustrate risks addressed or omitted.
If shortlisted, we negotiate the parts of the risk of the Plan during Tender.
If awarded the Project, then the final plan and methodology becomes the signed contract documents. Then we can all build one project.