## Sheet1
Concept
Brief
Feasibility Studies
Design
Design
Implementation
Tender
Construction
Handover | Handover
Choose the position and length of the blue boxes to suit Good commissioning practice
Appoint commissioning specialist
Plan for commisioning
Design for commisioning
Pre Commissioning
Prelim checks
Visual checks
Physical checks
Acceptance
Static Completion
Commissioning
Setting to work
Testing and Balancing
Performance Testing
Handover
User training
O&M manuals
Ongoing maintenance
Do Not Amend the Tasks or durations