###### 15th June 2010

Gibson O’Connor Ltd

54 Lunn Avenue, Mt Wellington .

PO Box 11200 Ellerslie,

Auckland 1542

Attention Mr Alan Wood

# Project Name :  Notification of Award – Glenfield Intermediate Dental Facilities

We have pleasure in awarding the Glenfield Intermediate Dental Fixed Facility Construction to Gibson O’Connor for the sum of Six Hundred and Four Thousand, Four Hundred and Fifty Four dollars ($604,454.00 ex GST), all as contained within Gibson O’Connor’s Tender and letter dated 3rd May 2010 to the Waitemata District Health Board and subsequent Tender clarifications.

The award shall be conditional upon the following;

- The Invitation to Tender Letter including the Tender Documents dated 21st April 2010;

- The Tender Documents Notices to Tenderers No’s 1, 2, 3 and 4;

- The Original Tender Bid Sum of $558,938 ex GST dated 3rd May 2010 with additional items dated 7th May 2010 sum to be added being;

  - Allowance for Sites being Tendered individually sum of $24,475

  - Allowance for APL Vantage Suite for Doors and Windows etc $3,767

  - Allowance to undertake power connection works via Vector Limited add $9,706

  - Allowance for illuminated signage add $7,568 ref Henderson Dental Sign K&K

  - Total of additions $604,454.00 ex GST.

- The Drawings and the Bill of Quantities shall be;

- Gibson O’Connor (GOC), Programme 28-4-10 start date 16th June 2010 subject to the approval of the Engineer to the Contract and Blessing being held 21st June on site Glenfield at 6:30 AM with Fence and Site offices and GOC Health and Safety already established on site for the digging in of the Mauri stone. Please revise programme to allow and submit to Rod Harvey prior to 21st June for acceptance.

- Forward bond certificate and Insurances in the required forms

- Forward the list of all staff and subcontractors names addresses and birthdates to be working on site for school BOT vetting immediate.

- Incorporation of Plumbing and Drainage Amendments Aurecon dated 17th May 2010 to  North Shore City Council and Leap Waterless Trap detail dated 14th May 2010

- Incorporating the additions and relocations of Power and Data points contained upon Kay and Keys Internal Elevations Sheet A3 Issue A; Internal Elevations Sheet A5 Issue A; Internal Elevations Sheet A6 Issue A; Internal Elevations Sheet A7 Issue A

- Notice Gen A requiring Duress Alarm required for both Reception and Treatment

  - Duress Alarm required for both Reception and Treatment

  - HVAC Electrical and Hydraulics shall be design Build

  - Use Timber Piles as detailed by Mitchell Vranges in conjunction with Woods

- Following North Shore Council requirements contained within Fire Safety Report by Aurecon dated 16th March 2010 JN 206281

- Observing H1 Calculation by Aurecon dated 23rd April 2010 confirming insulation

- Kay and Keys Tender Price Validity letter dated 26th May 2010

- Aurecon HVAC Elec Fire Hydraulics design changes

- Kay and Keys Architects changes

2.	BASIS OF APPOINTMENT

This letter of appointment and the Form Of Agreement attached.

Must issue separate claims and invoices for each project

3.	SCOPE OF CONSULTANT SERVICES

The scope and deliverables are as described in the attached documentation called Consultant Services all as contained within:

- This Letter

- Agreement Relating To Architect

- Architect’s Services Requirements

- Organisation Chart

- Equipment List

- Deeds of Lease for Henderson and Glenfield Intermediates and Edmonton Primary School

At the conclusion of each phase the specific written instruction from the Client is required for the services of the next phase to be undertaken.

4.	REMUNERATION

The professional fees and disbursements for the work carried out as described in section 3 above will be as outlined in the Agreement.

5.	PROGRAMME

The project programme is as described in the Services Agreement.  This will subsequently be refined with updated programmes as the project is progressed through development phases.

6.	GENERAL

We welcome Kay and Keys to the project and ask you to note Design Team Meetings set for 2PM Thursdays at Waitakere Hospital’s Snelgar House Level 2 for 1 PM starting 1st April.

Yours sincerely,

Rodney Harvey
Project Manager Oral Health
Child Women and Family Services
Waitemata District Health Board
Tel 09 486 8900
Mobile 021 659 382
Email Rodney.Harvey@waitematadhb.govt.nz